## Sheet1
SQA Test execution Status By WICER Summary
Code Drop | Priority |  | program Scope | Deployed in SQA Env | Planned till date for Execution | Completed | Failed + Blocked | WIP | Not Started | Not Started | % Completed
[9 empty] | (vs Planned till date) | (vs Deployed)
CD1.1 | P1 | Retrofit | 33 | 33 | 29 | 21 | 9 | 0 | 0 | 3 | 64%
| P2 | No Code Change with GxP & FUT | 58 | 58 | 26 | 18 | 20 | 2 | 0 | 18 | 31%
| P2-1 | No Code Change WICER(GXP)- No FUT | 54 | 54 | 16 | 11 | 12 | 1 | 0 | 30 | 20%
| P3 | No Code Change WICER- No FUT | 158 | 158 | 33 | 46 | 30 | 12 | 0 | 70 | 29%
CD1.1 Total |  |  | 303 | 303 | 104 | 96 | 71 | 15 | 0 | 121 | 32%
CD1.2 | P1 | Retrofit | 16 | 16 | 12 | 5 | 4 | 2 | 1 | 5 | 31%
| P2 | No Code Change with GxP & FUT | 24 | 24 | 19 | 4 | 7 | 2 | 6 | 11 | 17%
| P2-1 | No Code Change WICER(GXP)- No FUT | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0%
| P3 | No Code Change WICER- No FUT | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0%
CD1.2 Total |  |  | 40 | 40 | 31 | 9 | 11 | 4 | 7 | 16 | 23%
CD1.3 | P1 | Retrofit | 34 | 16 | 2 | 0 | 2 | 0 | 0 | 14 | 0%
| P2 | No Code Change with GxP & FUT | 15 | 24 | 1 | 0 | 1 | 0 | 0 | 23 | 0%
| P2-1 | No Code Change WICER(GXP)- No FUT | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0%
| P3 | No Code Change WICER- No FUT | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0%
CD1.3 Total |  |  | 49 | 40 | 3 | 0 | 3 | 0 | 0 | 37 | 0%
Grand Total |  |  | 392 | 383 | 138 | 105 | 85 | 19 | 7 | 174 | 27%
| Total | Incomplete |  |  |  | %Completed | WICERs remaining
NCC | 158 | 112 |  | Drop 1 | p1 | 63.64% | 12
[5 empty] | P2 | 25.89% | 83
|  | %completed |  |  | p3 | 29.11% | 112
34.2%
|  |  |  | Drop 2 | P1 | 31.25% | 11
[5 empty] | P2 | 16.67% | 20
[5 empty] | P3 | NA | NA
|  |  |  | Drop 3 | P1 | 0 | 49
[5 empty] | P2 | 0
[5 empty] | P3 | 0
[6 empty] | TC Remaining P1 & P2 | 1225 | Plus Regression & retest | 1470
|  |  |  | Avg TC/WICER | 7 | Total Remaining | 2009 | Plus Regression & retest | 2410.8
[6 empty] | Man Days required P1&P2 | 490 | Plus regression & retest | 588
[6 empty] | Man Days required P1-P3 | 803.6 | Plus Reg P1-P3 | 964.32
|  |  |  | SQA Test Engs. | 22.5 | Man days with Resourcing P1&P2 | 21.7778 | w/ Regression & Retest | 26.1333
|  |  |  | TC per Day executed | 2.5 | Man days with Resourcing P1-P3 | 35.7156 | w/ Regression & Retest | 42.8587
[7 empty] | P1-P2 | Adjusted for Automation | 26.1333
[8 empty] | Days remaining | 23
Extra Days | 1
WICERS Additional | 8.0357
|  |  |  | -3.1333 | 157.5
22.5
|  |  |  | Pre Int 1 | P1 | Retrofit | all
[5 empty] | P2 | GMP/FUT'ed | all
[5 empty] | P3 | NCC | 10

## P1 and P2 (GXP Only)
SQA Test execution Status By WICER Summary
Code Drop | Priority |  | program Scope | Deployed in SQA Env | Planned till date for Execution | Completed | Failed + Blocked | WIP | Not Started | Not Started | % Completed
[9 empty] | (vs Planned till date) | (vs Deployed)
CD1.1 | P1 | Retrofit | 33 | 33 | 29 | 21 | 9 | 0 | 0 | 3 | 64%
| P2 | No Code Change with GxP & FUT | 58 | 58 | 26 | 18 | 20 | 2 | 0 | 18 | 31%
| P2-1 | No Code Change WICER(GXP)- No FUT | 54 | 54 | 16 | 11 | 12 | 1 | 0 | 30 | 20%
| P3 | No Code Change WICER- No FUT | 158 | 158 | 33 | 46 | 30 | 12 | 0 | 70 | 29%
CD1.1 Total |  |  | 303 | 303 | 104 | 96 | 71 | 15 | 0 | 121 | 32%
CD1.2 | P1 | Retrofit | 16 | 16 | 12 | 5 | 4 | 2 | 1 | 5 | 31%
| P2 | No Code Change with GxP & FUT | 24 | 24 | 19 | 4 | 7 | 2 | 6 | 11 | 17%
| P2-1 | No Code Change WICER(GXP)- No FUT | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0%
| P3 | No Code Change WICER- No FUT | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0%
CD1.2 Total |  |  | 40 | 40 | 31 | 9 | 11 | 4 | 7 | 16 | 23%
CD1.3 | P1 | Retrofit | 34 | 16 | 2 | 0 | 2 | 0 | 0 | 14 | 0%
| P2 | No Code Change with GxP & FUT | 15 | 24 | 1 | 0 | 1 | 0 | 0 | 23 | 0%
| P2-1 | No Code Change WICER(GXP)- No FUT | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0%
| P3 | No Code Change WICER- No FUT | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0%
CD1.3 Total |  |  | 49 | 40 | 3 | 0 | 3 | 0 | 0 | 37 | 0%
Grand Total |  |  | 392 | 383 | 138 | 105 | 85 | 19 | 7 | 174 | 27%
[6 empty] | %Completed | WICERs remaining
|  |  |  | Drop 1 | p1 | 63.64% | 12
| Total GxP | GXP Incomplete |  |  | P2 | 25.89% | 43
P2 | 24 |  |  |  | p3 | 29.11% | 112
P2.1
|  |  |  | Drop 2 | P1 | 31.25% | 11
[5 empty] | P2 | 16.67% | 0
[5 empty] | P3 | NA | NA
|  |  |  | Drop 3 | P1 | 0 | 49
[5 empty] | P2 | 0
[5 empty] | P3 | 0
[6 empty] | TC Remaining P1 & P2 | 805 | Plus Regression & retest | 901.6
|  |  |  | Avg TC/WICER | 7 | Total Remaining | 1589 | Plus Regression & retest | 1906.8
[6 empty] | Man Days required P1&P2 | 287.5 | Plus regression & retest | 322
[6 empty] | Man Days required P1-P3 | 567.5 | Plus Reg P1-P3 | 681
|  |  |  | SQA Test Engs. | 16 | Man days with Resourcing P1&P2 | 17.9688 | w/ Regression & Retest | 20.125
|  |  |  | TC per Day executed | 2.8 | Man days with Resourcing P1-P3 | 35.4688 | w/ Regression & Retest | 42.5625
[7 empty] | P1-P2 | Adjusted for Automation | 13.0813 | remove 35% of deficit
[8 empty] | Days remaining | 23