## RICEW Tracker_1 (hidden)
| WICER Object Details | [9 empty] | Design | [6 empty] | Execution
old | RICEW ID | Description | Work Stream | Object Type | Priority | New/Retrofit/No code change required | New/Retrofit/No code change required - Revised | Test Cycle | Gilead Code Drop Bucket | FBD Completed (Yes/No) | FBD Completion date | Automation design completion (Y/N/Out of scope/Decommissioned) | Total Test Cases Planned | Full Automated TC Count | Partial Automation TC Count | Full manual TC Count | Design / Execution | Planned Execution date | Pre requisites start date mm/dd/yyyy | Pre Requisite end date mm/dd/yyyy | Revised Planned Start Date mm/dd/yyyy | Revised Planned End Date mm/dd/yyyy | Resource Name | Dependency | Manual/ Automation | Actual Test Execution date | Passed | Failed | Blocked | Not Completed | No Run | Defect id | Status | Execution In progress%
#REF! | ICE1 | EDI 844 Chargebacks (MODELN) | NONEBS-GEM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | ICE2 | EDI 845 Contracts (MODELN) | NONEBS-GEM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | ICE3 | EDI 849 Chargeback Reconciliations (MODELN) | NONEBS-GEM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | ICE4 | GEM - Common FTP Framework | NONEBS-GEM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPI1 | GILDA to cTP Clinical Trial interface (RND) | NONEBS-GEM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPI2 | cTP to GILDA Study Status interface (RND) | NONEBS-GEM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPI3 | RDMS to cTP file transfer (RND) | NONEBS-GEM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPI4 | cTP to RDMS file transfer (RND) | NONEBS-GEM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPI5 | EQMS to GxPLearn interface (RND) | NONEBS-GEM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPI6 | Outbound interface for sending shipment data from OBIEE to Integrichain and ValueCentric | NONEBS-GEM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EOTC125 | Customization of MSCA to allow for verification step to be added to order processing on MSCA. Customization of MSCA to Scan an item cross reference (barcode) & return the Item number on the Manifest Picking page. | OTC | E |  | Rewrite | Rewrite | INT1 | CD1.3 | FBD Completed | 2018-06-08 | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-08-03 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | WOTC45 | Workflow extension for Amount Based RMA approval | OTC | W |  | Rewrite | Rewrite | INT1 | CD1.3 | FBD Completed | 2018-05-24 | Automation completed | [5 empty] | 2018-08-05 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | WOTC95 | Workflow Extension for Order Approvals with Manual Discounts | OTC | W |  | Rewrite | Rewrite | INT1 | CD1.3 | FBD Completed | 2018-05-14 | Automation completed | [5 empty] | 2018-08-05 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | EOTC184 | WebADI Price List Maintenance extension | OTC | E |  | Rewrite | Rewrite | INT1 | CD2.1 | FBD Completed | 2018-05-19 | Out of scope | [5 empty] | 2018-08-03 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EOTC137 | Consolidated Invoice for Spain | OTC | E |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Out of scope | [5 empty] | 2018-06-26 | [6 empty] | Manual | 2018-06-26 | [6 empty] | Not Started | #VALUE!
#REF! | EOTC183 | Extension for Picking in Full Quantities for the Big 3 | OTC | E |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-05-31 | Automation completed | [5 empty] | 2018-07-02 | [6 empty] | Partial | 2018-06-26 | [6 empty] | Not Started | #VALUE!
#REF! | IOTC13 | Inbound Interface for Shipping Information from Third Party Logistics Provider (3PL) | OTC | I |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-05-22 | Automation completed | [5 empty] | 2018-07-06 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC172 | Japanese 3PL Pick Request Extract Report (Excel) | OTC | R |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-05-20 | Automation completed | [5 empty] | 2018-07-11 | [6 empty] | Partial | 2018-07-04 | [6 empty] | Not Started
#REF! | EOTC155 | MSCA - EBS-Axway Returns/RMA counterfeit and Recall Serialization Process (Master Component) | OTC | E |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-05-24 | Out of scope | [5 empty] | 2018-07-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EOTC163 | Greek Localization turnover report | OTC | E |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-05-22 | Automation completed | [5 empty] | 2018-07-10 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | EOTC174 | VAT Compliance Project | OTC | E |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | 2018-07-06 | Out of scope | 7 |  |  | 7 |  | 2018-08-01 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EOTC175 | Automatic Cash Application | OTC | E |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | 2018-07-06 | Out of scope | 7 |  |  | 7 |  | 2018-08-01 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IOTC152 | Outbound Interface to send Credit Memos for RMAs to GENCO | OTC | I |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-05-24 | Automation completed | [5 empty] | 2018-07-10 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IOTC158 | Attaching Pack Slips on Sales Order Header | OTC | I |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-06-13 | Automation completed | [5 empty] | 2018-07-11 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | IOTC170 | Japan Shikiro-Sho (Invoice) Information outbound | OTC | I |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-06-18 | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-07-11 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC139 | Receipt Application Invoice | OTC | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-07-27 | Automation completed |  |  | 2 | #VALUE! |  | 2018-07-11 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EOTC162 | Italy Autoadjustment wrapper | OTC | E |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Completed | 2018-05-09 | Automation completed | [5 empty] | 2018-08-03 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | EOTC181 | AR Transactions WebADI | OTC | E |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Completed | 2018-05-16 | Out of scope | [5 empty] | 2018-08-03 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IOTC12_120 | Inbound Interface for Clinical IVX | OTC | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Completed | 2018-06-05 | Automation completed | [5 empty] | 2018-08-03 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IOTC121 | Sales orders and credit information outbound to Model N | OTC | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-13 | Out of scope | 7 |  |  | 7 |  | 2018-07-31 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IOTC135 | CR 518 EDI 856 Advanced Ship Notices | OTC | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Completed | 2018-06-04 | Automation completed | [5 empty] | 2018-08-03 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | IOTC151 | Inbound Interface to create RMAs via EDI 180 from GENCO | OTC | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Completed | 2018-05-24 | Automation completed | [5 empty] | 2018-08-03 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IOTC180 | Poland Invoice Outbound Interface to National Authorities | OTC | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-13 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IOTC3 | Inbound Interface for Electronic Sales Order | OTC | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Completed | 2018-05-07 | Automation completed | [5 empty] | 2018-08-03 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | IOTC5 | Outbound Interface for Electronic Invoices to Customers | OTC | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-20 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC136 | Localized Invoice layout for Poland | OTC | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-27 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC190 | WebADI Approval Management Report | OTC | R |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-08-10 | Out of scope | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | ROTC83 | Customer Facing Output for Pack Slip | OTC | R |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Completed | 2018-07-27 | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-08-04 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC85 | Customer facing document for commercial invoice | OTC | R |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Completed | 2018-06-16 | Pending Automation Design |  |  | 22 |  |  | 2018-08-04 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | WOTC183 | WebADI Approval Workflow | OTC | W |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Completed | 2018-05-16 | Out of scope | [5 empty] | 2018-08-04 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EOTC178 | GIL DSCSA Web Portal (ADF) | OTC | E |  | Retrofit | Retrofit | INT1 | CD2.1 | FBD Completed | 2018-06-02 | Out of scope | [5 empty] | 2018-08-03 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | ROTC151 | GIL DQSA Shipping Compliance Report | OTC | R |  | Retrofit | Retrofit | INT1 | CD2.1 | FBD Completed | 2018-06-02 | Automation completed | [5 empty] | 2018-07-11 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EOTC134 | Auto Invoice Pre-processor extension | OTC | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-08 | Automation completed | [5 empty] | 2018-07-10 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | EOTC153 | EBS-Axway Complete Lot Ship(South Korea) | OTC | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-02 | Automation completed | [5 empty] | 2018-07-04 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EOTC166 | Automate Logical Receipt for EDI RMAs | OTC | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-24 | Automation completed | [5 empty] | 2018-07-04 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | EOTC53 | Extension to Automatically Generate Accounting Entries for System Generated Accruals | OTC | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-22 | Automation completed | [5 empty] | 2018-07-10 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | EOTC63 | France Quota Rollover Extension | OTC | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-17 | Automation completed | [5 empty] | 2018-07-05 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | EOTC111 | Ability to determine the location segment value of the AR/revenue account based on the transaction (sales order line) ship to location | OTC | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-22 | Out of scope | [5 empty] | 2018-07-02 | [6 empty] | Manual | 2018-07-02 | [6 empty] | Not Started | #VALUE!
#REF! | EOTC123 | Intrastat custom PL.SQL | OTC | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-11 | Automation completed | [5 empty] | 2018-07-10 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EOTC138 | Automate Clinical Customer Creation | OTC | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-05 | Automation completed | [5 empty] | 2018-07-04 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EOTC144 | Customer data extract to EDQ | OTC | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-05 | Automation completed | [5 empty] | 2018-07-04 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EOTC159 | VAT triangulation for Luxembourg | OTC | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-22 | Automation completed | [5 empty] | 2018-07-03 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EOTC160 | Italy eInvoice Forms personalization | OTC | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-17 | Automation completed | [5 empty] | 2018-07-10 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | EOTC161 | Download Attachments from Oracle Forms | OTC | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-08 | Automation completed | [5 empty] | 2018-07-04 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EOTC165 | Enable ASN transmission for manual Ship confirmation | OTC | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-31 | Automation completed | [5 empty] | 2018-07-02 | [6 empty] | Automation | 2018-07-02 | [6 empty] | Not Started | #VALUE!
#REF! | EOTC168 | GIL Sales Agreement Upload | OTC | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-05 | Out of scope | [5 empty] | 2018-07-02 | [6 empty] | Manual | 2018-07-02 | [6 empty] | Not Started | #VALUE!
#REF! | EOTC169 | Automatic Holds and Booking for US Commercial EDI /Manual Order | OTC | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-07 | Automation completed | [5 empty] | 2018-07-10 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | EOTC179 | GIL DSCSA Portal Scheduler | OTC | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-02 | Out of scope | [5 empty] | 2018-07-04 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EOTC180 | GIL DSCSA Portal Utility Program | OTC | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-02 | Out of scope | [5 empty] | 2018-07-04 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EOTC182 | Customers and Sites WebADI | OTC | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-05 | Out of scope | [5 empty] | 2018-07-03 | [6 empty] | Manual | 2018-07-03 | [6 empty] | Not Started | #VALUE!
#REF! | EOTC186 | EU Shipping Serial Number Capture Program | OTC | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-03 | Automation completed | [5 empty] | 2018-07-10 | [6 empty] | Automation | 2018-07-03 | [6 empty] | Not Started
#REF! | EOTC187 | MSCA Scanning for Exception Export Orders (New MSCA Screen) | OTC | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-03 | Out of scope | [5 empty] | 2018-07-04 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IOTC10 | Inbound Interface for AR Credit Memos from Model N | OTC | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-07-06 | Automation completed | [5 empty] | 2018-07-25 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IOTC109 | Outbound Interface for Pick Requests to Third Party Logistics Provider (3PL) | OTC | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Automation completed | [5 empty] | 2018-07-25 | [6 empty] | Partial | 2018-07-03 | [6 empty] | Not Started
#REF! | IOTC110 | Inbound interface from non-US Banks for receipts / payments | OTC | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-06 | Out of scope | 7 |  |  | 7 |  | 2018-07-31 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IOTC112 | Outbound interface for Sales data to MOH - Italyprocess notification to the customer | OTC | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-16 | Automation completed | [5 empty] | 2018-07-06 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IOTC119 | Interface for Direct debit request to bank of America | OTC | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-06 | Out of scope | 7 |  |  | 7 |  | 2018-07-31 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IOTC145 | Customer Outbound | OTC | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-13 | Out of scope | 7 |  |  | 7 |  | 2018-07-31 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IOTC147 | Turkey e-Invoice Dispatch Note number inbound from Zet Farma | OTC | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-22 | Automation completed | [5 empty] | 2018-07-06 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IOTC149 | RMA Counterfeit Check Interface | OTC | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-24 | Out of scope | [5 empty] | 2018-07-09 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IOTC15 | Outbound Interface for Shipment Confirmation to GILDA | OTC | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-04 | Automation completed | [5 empty] | 2018-07-06 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IOTC153 | Inbound Interface for processing Debit Memo files for GENCO RMAs | OTC | I |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-24 | Automation completed | [5 empty] | 2018-07-06 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | IOTC154 | Outbound Interface for sending Order Info for Min-Max Evaluation | OTC | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-14 | Automation completed | [5 empty] | 2018-07-06 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IOTC155 | Inbound Interface to receive Order Recommendations and update/Book Order | OTC | I |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-14 | Automation completed | [5 empty] | 2018-07-06 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IOTC16 | Outbound Interface for AR Credit Memo Information to Model N | OTC | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-13 | Out of scope | 7 |  |  | 7 |  | 2018-07-31 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IOTC179 | Outbound Interface for Spain SII AR Invoice Tax Details | OTC | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-13 | Out of scope | 7 |  |  | 7 |  | 2018-07-31 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IOTC29 | Ability to electronically provide various information: lot/serial information, price, etc. (GERS, ePedigree, Turkish tracking requirements, Italian tracking system etc.) during the ship confirm process notification to the customer | OTC | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | [5 empty] | 2018-07-06 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC116 | France GERS reconcillation report | OTC | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-20 | Automation completed | [5 empty] | 2018-07-02 | [6 empty] | Partial | 2018-07-03 | [6 empty] | Not Started | #VALUE!
#REF! | ROTC118 | Daily Sales Reporting Extraction Report | OTC | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-08 | Automation completed | [5 empty] | 2018-07-11 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC122 | Customer Master Change Tracking Report | OTC | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-05 | Automation completed | [5 empty] | 2018-07-02 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC124 | Sales Order Acknowledgement and RGA CFD Report | OTC | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-16 | Automation completed | [5 empty] | 2018-07-11 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC128 | Sales and shipment data extract from EBS to MOH in Turkey | OTC | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-20 | Automation completed | [5 empty] | 2018-07-02 | [6 empty] | Partial | 2018-07-03 | [6 empty] | Not Started
#REF! | ROTC131 | UGA Report - Reconciliation with GERS file | OTC | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-08 | Automation completed | [5 empty] | 2018-07-11 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC132 | Monthly and "As of" + "date to date" statements with PO customer number | OTC | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | [5 empty] | 2018-07-11 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | ROTC140 | Credit Note Matching Invoice Report | OTC | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-09 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | ROTC141 | Customer Extract | OTC | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-05 | Automation completed | [5 empty] | 2018-07-02 | [6 empty] | Partial | 2018-07-03 | [6 empty] | Not Started | #VALUE!
#REF! | ROTC142 | To run report from EBS showing the active Advance Pricing modifiers including rates, start and term dates, product codes, modifier name and G/L Accounts, legal entity, NDCs and qualifiers. | OTC | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-19 | Automation completed | [5 empty] | 2018-07-11 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC146 | Direct Debit Prenotification letter | OTC | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-06 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | ROTC148 | Spanish Modelo340 requirement | OTC | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-06 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | ROTC156 | RMA Counterfeit Report | OTC | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | 4 |  | 4 |  |  | 2018-07-20 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC167 | GIL Quota Consumption Report | OTC | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-07 | Automation completed | [5 empty] | 2018-07-11 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC171 | Japanese Consolidate Customer Invoice | OTC | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-07-20 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC173 | Japaneser Shikiro-Sho Report | OTC | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-07-20 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC176 | GIL EOF Local FDA Report - (Greece) | OTC | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | [5 empty] | 2018-07-11 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC177 | GIL DSCSA Portal Activity Report | OTC | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-02 | Automation completed | [5 empty] | 2018-07-11 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC178 | Price List Maintenance Report | OTC | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-19 | Automation completed | [5 empty] | 2018-07-20 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | ROTC188 | Sales Order Shipping Forecast Report | OTC | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-03 | Automation completed | [5 empty] | 2018-07-11 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC51 | Customer Facing Output for RMA Authorization | OTC | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed |  |  | 6 | #VALUE! |  | 2018-07-19 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ROTC81 | Customer Facing Output for Order Fulfillment Request to Third Party Logistics Provider (3PL) | OTC | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | NEW | Order Management HTML Interface-New Customization - Form Personalization | OTC | E |  | New | New | INT2 | CD1.3 | FBD Pending | 2018-07-20 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | NEW | Move existing form personalization from Order Organizer form to Order Management HTML Interface | OTC | E |  | New | New | INT2 | CD1.3 | FBD Pending | 2018-07-20 | Out of scope | 7 |  |  | 7 |  | 2018-08-01 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | NEW | Pricing upload using WEBADI Excel sheet | OTC | E |  | New | New | INT2 | CD2.1 | FBD Pending | 2018-07-20 | Out of scope | 7 |  |  | 7 |  | 2018-08-01 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | NEW | OIP Portal Changes | OTC | E |  | New | New | INT2 | CD2.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-01 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | NEW | Shipping Transactions HTML Interface -New Customization - Form Personalization | OTC | E |  | New | New | INT2 | CD2.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-01 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | COTC100 | Customer Conversion | OTC | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | COTC101 | Open AR Transactions Conversion | OTC | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EOTC152 | GIL DQSA Shipping Exception Notification | OTC | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EOTC154 | Serialization 2D scanning | OTC | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EOTC164 | Dubline Direct Distribution Project | OTC | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IOTC12 | Inbound Interface for Sales Order from GILDA | OTC | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IOTC150 | ASN TI/TH/TS Receipt Acknowledgment | OTC | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IOTC171 | Outbound interface between OBIEE and Integrichain (OBIEE) | OTC | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | ROTC166 | GIL 3PL Ship confirmation reconciliation report | OTC | R |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | ROTC189 | Serial Number Capture Report | OTC | R |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | ROTC59 | EBS Report for Days Sales Outstanding by Entity and Customer | OTC | R |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | WOTC96 | Workflow Extension for Logical Receiving of RMAs from GENCO | OTC | W |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | WMGR1 | Project Budget Approval workflow customization | PRJ | W |  | Rewrite | Rewrite | INT1 | CD1.3 | FBD Completed | 2018-05-21 | Out of scope | [5 empty] | 2018-08-04 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EMGR29 | Project Budject inbound from Hyperion to EBS (OPC) | PRJ | E |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | [5 empty] | 2018-07-04 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ERTR107 | Projects Approval WF | PRJ | E |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Out of scope | [5 empty] | 2018-06-26 | [6 empty] | Manual | 2018-06-26 | [6 empty] | Not Started
#REF! | RMGR15 | Oracle Alert to check a PO against a project budget | PRJ | R |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-05-21 | Automation completed | [5 empty] | 2018-07-06 | [6 empty] | Partial | 2018-07-04 | [6 empty] | Not Started
#REF! | ERTR120 | Enhancement for Open Commitment in OPC | PRJ | E |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-06-13 | Automation completed |  |  | 8 | 6 |  | 2018-07-10 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IRTR93b | Interface of Projects data from DRM to EBS (middleware to EBS) | PRJ | I |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-05-18 | Out of scope | [5 empty] | 2018-07-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | RRTR116 | Custom POET to COA reconciliation report | PRJ | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-06-12 | Pending Automation Design |  |  | 14 |  |  | 2018-07-13 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RRTR54 | Complete Audit trail on who changes the status of a project | PRJ | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-06-12 | Automation completed |  |  | 5 |  |  | 2018-07-13 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RRTR59 | Custom concurrent program to populate FA_MASS_ADDITIONS | PRJ | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-06-12 | Automation completed | [5 empty] | 2018-07-18 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ERTR100 | Extension to transfer Manufacturing WO Cost from OPM to Project Cost | PRJ | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | [5 empty] | 2018-07-05 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ERTR110 | Extract data directly from OPC for Hyperion Projects load - POC only | PRJ | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Pending Automation Design | 7 |  | 0 | 7 |  | 2018-08-02 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ERTR112 | Capital Asset metadata Automation from DRM to OPC | PRJ | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Pending Automation Design | 7 |  | 0 | 7 |  | 2018-08-02 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ERTR115 | Custom WEBADI Template - CR 1615 | PRJ | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Out of scope | [5 empty] | 2018-07-09 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | ERTR119 | WEBADI for Batch upload of CIP asset capitalization | PRJ | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-07-09 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ERTR123 | Extension for interest capitalization | PRJ | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | [5 empty] | 2018-07-05 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | ERTR92 | Projects Auto accounting (SQL queries | PRJ | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Out of scope | [5 empty] | 2018-07-09 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IRTR105 | Project Hours Kronos to EBS | PRJ | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-07-19 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IRTR93a | Projects Outbound Interface | PRJ | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-18 | Out of scope | [5 empty] | 2018-07-19 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IRTR95 | Costs by projects from ADP Payroll to EBS | PRJ | I |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed |  | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-07-19 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IRTR98a | Interface of Project Status to DRM (EBS to middleware) | PRJ | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-18 | Out of scope | [5 empty] | 2018-07-19 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IRTR98b | Interface of Project Status to DRM (Middleware to DRM) | PRJ | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-18 | Out of scope | [5 empty] | 2018-07-20 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | RRTR106 | OPC/GL Reconciliation Report | PRJ | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Pending Automation Design |  |  | 4 |  |  | 2018-07-13 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RRTR118 | Projects month end reconciliation reports | PRJ | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Automation completed | [5 empty] | 2018-07-16 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RRTR36 | Report to reconcile project cost with associate GL code | PRJ | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Automation completed | [5 empty] | 2018-07-17 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RRTR37 | Report to reconcile GL trial balance broken out by project | PRJ | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Automation completed | [5 empty] | 2018-07-17 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RRTR39 | Report to show project costs by legal entity | PRJ | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Automation completed | [5 empty] | 2018-07-18 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RRTR42 | Report to track R&D costs nationally by state | PRJ | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Automation completed | [5 empty] | 2018-07-18 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RRTR43 | Ability to track project cost by responsible person | PRJ | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Automation completed | [5 empty] | 2018-07-18 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RRTR52 | Report to list all open PO's by project | PRJ | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Automation completed | [5 empty] | 2018-07-18 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RRTR88 | CIP Account Reconciliation – Projects Report | PRJ | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Automation completed | [5 empty] | 2018-07-18 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RRTR99 | Reconciliation report for PO and Receipt Cost | PRJ | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Automation completed | [5 empty] | 2018-07-18 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | CRTR80 | Conversion of Open Projects | PRJ | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CRTR81 | Conversion of Project Balances | PRJ | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | RMGR10 | Report for mapping between historical and future project number | PRJ | R |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | RRTR113 | Project Receiving Status Report | PRJ | R |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTM234 | Intercompany COGS Workflow customization | PTM | W |  | Rewrite | Rewrite | INT1 | CD1.3 | FBD Completed | 2018-05-31 | Out of scope | [5 empty] | 2018-08-03 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | WPTM111 | Item Creation and change Workflow | PTM | W |  | Rewrite | Rewrite | INT1 | CD1.3 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | WPTM115 | detailed Sub ledger Report By Document Type | PTM | W |  | Rewrite | Rewrite | INT1 | CD1.3 | FBD Pending | 2018-07-20 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | WPTM238 | Signature Type Signing Reason LOV Change | PTM | W |  | Rewrite | Rewrite | INT1 | CD1.3 | FBD Completed | 2018-06-07 | Automation completed | [5 empty] | 2018-08-05 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | EPTM197 | Receiving information to Loftware | PTM | E |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-06-06 | Out of scope | [5 empty] | 2018-07-04 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM264 | FCIM Dispensing Material Label | PTM | E |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Out of scope | [5 empty] | 2018-07-04 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM272 | CMO PO, WO Sync using Webadi | PTM | E |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-06-07 | Out of scope | [5 empty] | 2018-06-26 | [6 empty] | Manual | 2018-06-26 | [6 empty] | Not Started | #VALUE!
#REF! | EPTM273 | Gilead Work Order Mass Update | PTM | E |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-06-06 | Out of scope | [5 empty] | 2018-06-26 | [6 empty] | Manual | 2018-06-26 | [6 empty] | Not Started | #VALUE!
#REF! | EPTM73 | Potency Based Component Availability Report | PTM | E |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Pending | 2018-07-06 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IPTM275 | Part Interface(Item) EBS --> KINAXIS | PTM | I |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-06-18 | Out of scope | [5 empty] | 2018-07-04 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTM276 | Onhand EBS --> KINAXIS | PTM | I |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed |  | Out of scope | [5 empty] | 2018-07-04 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTM277 | Purchase Order EBS --> KINAXIS | PTM | I |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Out of scope | [5 empty] | 2018-08-05 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTM284 | Sourcing Rule EBS --> KINAXIS | PTM | I |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-06-18 | Out of scope | [5 empty] | 2018-08-05 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTM289 | Interface to bring Resource Downtimes data from Maximo to ASCP | PTM | I |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Pending | 2018-07-13 | Pending Automation Design | 7 |  | 6 | 1 |  | 2018-08-05 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM180 | In transit Inventory Report | PTM | R |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | 2018-07-05 | [6 empty] | Partial
#REF! | RPTM256 | CMO Open Order Report | PTM | R |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed |  | Automation completed | 6 |  | 6 | 0 |  | 2018-07-05 | [6 empty] | Partial | 2018-07-03 | [6 empty] | Not Started | #VALUE!
#REF! | RPTM257 | CMO Delivery Metrics Report | PTM | R |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed |  | Automation completed |  |  | 7 | #VALUE! |  | 2018-07-05 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM258 | CMO Inventory Planning Report | PTM | R |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed |  | Automation completed |  |  | 9 | #VALUE! |  | 2018-07-05 | [6 empty] | Partial | 2018-07-03 | [6 empty] | Not Started | #VALUE!
#REF! | RPTM261 | GIL Lot Genealogy Report with Operations | PTM | R |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed |  | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-07-05 | [6 empty] | Partial | 2018-07-03 | [6 empty] | Not Started | #VALUE!
#REF! | RPTM264 | Gilead Lot Status Report | PTM | R |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | 2018-07-04 | [6 empty] | Not Started
#REF! | RPTM290 | Report to generate Resource Downtime Overlapping report | PTM | R |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Out of scope |  |  | 2 |  |  | 2018-07-05 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM292 | Gilead On Hand Report by Location and Time | PTM | R |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-06-05 | Automation completed | [5 empty] | 2018-07-05 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM52 | Cycle Count & Physical Inventory Corrections Report | PTM | R |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-06-18 | Automation completed | [5 empty] | 2018-07-05 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | WPTM215 | QA Notification program | PTM | W |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-05-22 | Out of scope | 3 |  |  |  |  | 2018-07-02 | [6 empty] | Manual | 2018-07-02 | [6 empty] | Not Started | #VALUE!
#REF! | EPTM235 | PTM Operatinal Views | PTM | E |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-05-31 | Out of scope | [5 empty] | 2018-07-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM253 | Accounting for purchase price variance (PPV) | PTM | E |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | 2018-07-06 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTM255 | Cost Calendar Setup | PTM | E |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | 2018-07-06 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTM304 | Views to extract Item, Supplier, Lot information for GLIMS integration | PTM | E |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-05-31 | Out of scope | [5 empty] | 2018-07-10 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | RPTM183 | Lot Trace Track Report | PTM | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-05-25 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM211 | Customization to standard report , "Period Close Pending Transactions Report" | PTM | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-05-09 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM232 | Inventory Transactions Report for Period Close | PTM | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-05-09 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM233 | Labor Hours Report for Period Close | PTM | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-05-09 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM246 | Modify layout of detail sub-ledger report and detail sub-ledger report by document type | PTM | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTM265 | Report to identify Data issues and Exceptions in PS to work as intended | PTM | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-05-25 | Out of scope |  |  | 2 |  |  | 2018-07-13 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM305 | GIL Organization Setup Evidence Report | PTM | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTM193 | MES Work Order Extension | PTM | E |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | IPTM144 | Material Transactions Inbound Interface(Inv Decr) | PTM | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | IPTM166 | Lot Status Change Outbound - To EBS (Werum) | PTM | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | IPTM2 | MES Material Transactions outbound to MES | PTM | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | IPTM27 | Items Outbound Interface | PTM | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | IPTM280 | Work Orders Prod EBS --> KINAXIS | PTM | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | IPTM283 | PO Requisitions EBS --> KINAXIS | PTM | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | IPTM3 | WO Information - Outbound | PTM | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-13 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IPTM314 | outbound interface to publish forecast and history data | PTM | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-13 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IPTM315 | GIL Planned Orders (WO) Inbound interface from Kinaxis to EBS | PTM | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-13 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IPTM5 | Report Routing Step on the WO - Inbound | PTM | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTM313 | Barcoded Pick List Report for Move Orders | PTM | R |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-20 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTM242 | Preclude Inventory | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-17 | Automation completed | [5 empty] | 2018-07-10 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | EPTM298 | CR-1652 Hide Parent Lot field in Receiving | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Automation completed | [5 empty] | 2018-07-10 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | EPTM58 | Lot Status Change Workflow | PTM | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-07 | Automation completed | [5 empty] | 2018-07-05 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | IPTM272 | Outbound Interface to send Lot information associated with Sales Orders to GENCO | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-22 | Automation completed | [5 empty] | 2018-07-06 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM121 | Labor Hours Analysis Report | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM187 | Open Work Orders Report | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM244 | Manual Report for Picking | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM262 | GIL INV EH&S Report | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM291 | Gilead Work Order Batch Production Schedule Report | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | CPTM148 | OPM Formula Conversion | PTM | C |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-07-31 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | CPTM151 | Item Cost Conversion | PTM | C |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-07-31 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | CPTM169 | Conversion of Routing | PTM | C |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-07-31 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | CPTM170 | Conversion of Recipes | PTM | C |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-07-31 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM112 | Item Creation Form and approval workflow status view | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTM177 | Custom SLA Source | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-07-31 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM178 | Automatic numbering for Inter-Org transfers | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-17 | Automation completed | [5 empty] | 2018-07-02 | [6 empty] | Automation | 2018-07-02 | 4 | [5 empty] | Pending | #VALUE!
#REF! | EPTM194 | Extension to Update the recipe id of the planned batch released from planning to a production recipe based on the Product & batch size | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-07-31 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM195 | Custom allocation Program & Report that allocates API onhand and updates API Batch Ingredient usage based on certain criteria such as Start date, batch no ,Item etc. | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-07-31 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM196 | Sampling information to Loftware | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-06 | Out of scope | [5 empty] | 2018-07-04 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM199 | Restrict generation of statistical forecast to IAO products((Demantra) | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-07-31 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM204 | Extension for Automatic lot status change for EU inter-org transfers | PTM | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-08 | Automation completed | [5 empty] | 2018-07-02 | [6 empty] | Automation | 2018-07-02 | 9 | [5 empty] | Pending | #VALUE!
#REF! | EPTM205 | Extension to Capture lot status and expiration date during material transaction | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-17 | Automation completed | [5 empty] | 2018-07-02 | [6 empty] | Partial | 2018-07-02 | [6 empty] | Not Started | #VALUE!
#REF! | EPTM208 | Extension to print status labels for Edmonton | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-01 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM209 | Custom program to calculate the PPV (difference between standard cost amount on the CMO WO and the list price on the purchase order) and create a journal in GL | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-01 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM213 | Customization to standard program ,"Lot and Serial Date notification Program" | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-01 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM216 | MSCA modifications | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-22 | Out of scope | [5 empty] | 2018-07-03 | [6 empty] | Manual | 2018-07-03 | [6 empty] | Not Started
#REF! | EPTM219 | Automate WO close – Given a data range and list of organizations, use standard API to close WOs in completed status. | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Automation completed | [5 empty] | 2018-07-02 | [6 empty] | Partial | 2018-07-02 | [6 empty] | Not Started | #VALUE!
#REF! | EPTM245 | Export Actual Production Units from EBS to Hyperion | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-01 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM260 | Inventory Adjustments | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-22 | Out of scope | [5 empty] | 2018-07-06 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM262 | Oceanside Workorder label | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Out of scope | [5 empty] | 2018-07-06 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM265 | EBS Messaging Framework | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-01 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM266 | Serialization Scan Query Update Extension | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-01 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM274 | Ocean Side Production Operator Role Configuration | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTM295 | EBS WMS setups for La Verne Organizations | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-07 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM297 | CR-1675 Warning Message upon Receipt of same Item-Lot combination | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Automation completed | [5 empty] | 2018-07-02 | [6 empty] | Automation | 2018-07-02 | [6 empty] | Not Started | #VALUE!
#REF! | EPTM299 | Operation Description update for workorders in PS | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-07 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM300 | Email notification extension in Demantra | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-07 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM301 | Custom Request Set Collections in ASCP | PTM | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-06 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTM302 | Control of Shipping and Receipt of Quarantine Finished Goods | PTM | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-18 | Automation completed | [5 empty] | 2018-07-02 | [6 empty] | Automation | 2018-07-02 | [6 empty] | Not Started | #VALUE!
#REF! | EPTM305 | Purge process for integrated supply chain (ISC) | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-07 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM306 | Extension for creating custom schema/views for integreation with Discoverant | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-07 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM307 | Web ADI for Uploading Forecast Data to Demantra | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-08 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM308 | Removing Combination in Demantra | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-08 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM309 | UOM Conversion in Demantra | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-08 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM69 | Lot Number Adopt/Assign Program | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTM76 | Vendor Lot Number - Mandatory Field Process | PTM | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-08 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTM164 | WO Completion - Inbound | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | IPTM167 | Send WO and Project Information - Outbound (Kronos) | PTM | I |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Automation completed |  |  | 2 |  |  | 2018-07-19 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTM192 | Send on-hand balance information (item, lot, location, LPN and quantity) to MES for reconciliation. | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | IPTM206 | LIMS to EBS inbound interace | PTM | I |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-09 | Out of scope | [5 empty] | 2018-07-19 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTM247 | EBS to LIMS Outbound Interface for Synchronization of Vendor Site ID Codes | PTM | I |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-06 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IPTM259 | Event Publishing Interface (EBS to Axway) | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-22 | Out of scope | [5 empty] | 2018-07-19 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTM267 | Scan Query Update Interface (Serialization) | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-22 | Out of scope | [5 empty] | 2018-07-19 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTM268 | Automated Trigger for QP Release (Serialization) | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Pending Automation Design | 7 |  |  | 7 |  | 2018-08-09 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTM270 | South Korea Reporting (Serialization) | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Pending Automation Design | 7 |  |  | 7 |  | 2018-08-09 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTM278 | Sales Orders EBS --> KINAXIS | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | IPTM279 | Work Orders Ingredients EBS --> KINAXIS | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | IPTM281 | Calenders EBS --> KINAXIS | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | IPTM287 | Forecast Interface Outbound | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-10 | Out of scope | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTM294 | EPCIS event publish to External systems – Gilead Publishes commissioning, Order Release, destroying events to Astellas | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-22 | Out of scope | [5 empty] | 2018-07-20 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTM295 | Upload supply Commit into Demantra | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-10 | Out of scope | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTM297 | Item Interface from GPLM to EBS | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Out of scope | [5 empty] | 2018-07-20 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTM299 | GIL API Schedule Outbound interface from EBS to Kinaxis | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Out of scope | [5 empty] | 2018-07-20 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTM313 | GIL Purchase Requisition (Planned Orders) Inbound interface from Kinaxis to EBS | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | IPTM7 | KRONOS inbound interface | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-10 | Out of scope | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTM8 | Lot and Item Detail Data Interface to LIMS | PTM | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-10 | Out of scope | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | RPTM104 | QC/QA Test Material Prioritization Report | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM105 | Lot Release Cycle Time Report | PTM | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-05 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM108 | Lot Value for Reserves Report | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTM179 | Detailed Sub ledger Report By Document Type | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTM181 | Inventory Roll forward | PTM | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-09 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM182 | Lot Shipment Report | PTM | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-13 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM184 | Lot Transaction History Report | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTM185 | On hand Inventory Balance Report | PTM | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-09 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM186 | Perpetual Inventory Report | PTM | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-09 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM188 | Work Order History Report | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM190 | Work Order Pick List Report | PTM | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-07 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM191 | CMO Work Order Pick List Report | PTM | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-06 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM210 | WO operations report to list all operations with bar code | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTM212 | Report to list transactions that have not been accounted by OPM | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-09 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | 2018-07-03 | [6 empty] | Not Started | #VALUE!
#REF! | RPTM220/224 | Physical Inventory Adjustment and Physical Inventory Tag Report | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | 2018-07-03 | [6 empty] | Not Started
#REF! | RPTM221 | Audit Trail Reports for QA to report on changes to master data - Item | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTM222 | Audit Trail Reports for QA to report on changes to master data - Lot | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTM223 | Audit Trail Reports for QA to report on changes to master data - Formula | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTM231 | Audit Trail Reports for QA to report on changes to master data - Supplier | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTM236 | Lot Genealogy Report | PTM | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-20 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM237 | Custom GXP report for RMA related information | PTM | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed |  | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-07-19 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM243 | Lot Recall Report | PTM | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Pending Automation Design |  |  | 10 |  |  | 2018-07-13 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM248 | Cycle Count Progress Report & Cycle count recount report | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-06 | Automation completed | [5 empty] | 2018-07-02 | [6 empty] | Partial | 2018-07-02 | [6 empty] | Not Started | #VALUE!
#REF! | RPTM249 | Lot Genealogy Functionality GAP | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-10 | Out of scope | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | RPTM250 | Oracle mechanism to alert for certain reportable events | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTM263 | GIL Work Order Supply and Demand Report | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Automation completed | [5 empty] | 2018-07-02 | [6 empty] | Partial | 2018-07-02 | [6 empty] | Not Started | #VALUE!
#REF! | RPTM303 | Report to print ASN details visible to warehouse technician | PTM | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-05 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM304 | GIL EBS Transaction Quantity Report by Location and Date Range | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | 2018-07-02 | [6 empty] | Not Started
#REF! | RPTM312 | BR100 Automation Excel Reports | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTM47 | Items Not Classified (ABC) Report | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-25 | Automation completed | [5 empty] | 2018-07-12 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM48 | Cycle Count Accuracy Report | PTM | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-10 | Out of scope | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | RPTM68 | Lot Re-Test/Expiry Date Detail Report | PTM | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-05 | Automation completed | [5 empty] | 2018-07-16 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM80 | Cycle Time Report | PTM | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-18 | Automation completed | [5 empty] | 2018-07-16 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | WPTM239 | Custom Notification on movement of Quarantine material to production area | PTM | W |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-16 | Out of scope | [5 empty] | 2018-07-18 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | WPTM54 | Cycle Count Approval & Adjustment Workflow | PTM | W |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-20 | Pending Automation Design | 7 |  | 6 | 1 |  | 2018-07-02 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IPTM203 | Collect shipment history from EBS to Demantra | PTM | I |  | Retrofit | No code change required | INT1 | CD1.2 | FBD Pending | 2018-07-06 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IPTM296 | EMEA Demand Planning - Demantra | PTM | I |  | Retrofit | No code change required | INT1 | CD1.2 | FBD Pending | 2018-07-13 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTM189 | Supplier Forecast Report. | PTM | R |  | Retrofit | No code change required | INT1 | CD1.2 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | NEW | New web based portal for receiving materials from internal and external sources – Personalization 1 | PTM | E |  | New | New | INT2 | CD2.1 | FBD Pending | 2018-07-13 | Out of scope | 7 |  |  | 7 |  | 2018-08-01 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | NEW | New web based portal for receiving materials from internal and external sources – Extension 1 | PTM | E |  | New | New | INT2 | CD2.1 | FBD Pending | 2018-07-13 | Out of scope | 7 |  |  | 7 |  | 2018-08-01 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | NEW | New web based portal for receiving materials from internal and external sources – Personalization 2 | PTM | E |  | New | New | INT2 | CD2.1 | FBD Pending | 2018-07-13 | Out of scope | 7 |  |  | 7 |  | 2018-08-01 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | CPTM147 | Item Conversion | PTM | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CPTM150 | Item Category Conversion | PTM | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CPTM156 | On-Hand Balances Conversion | PTM | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CPTM159 | Lot Master Conversion | PTM | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CPTM168 | Conversion of Sourcing Rules | PTM | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CPTM198 | Shipment history from JDE to Demantra conversion | PTM | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CPTM263 | Item Org Assignment Conversion | PTM | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTM251 | Add Reporting UOM to APCC | PTM | E |  | Decommissioned | Decommissioned | N/A | N/A | FBD Completed | 2018-05-25 | Out of scope | [5 empty] | 2018-08-04 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTM269 | Serial Transaction Query | PTM | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTM292 | Receiving Form (MSCA and Oracle) Extension for Parent Lot Number | PTM | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTM296 | Materialized View - Put away WMS Rule for La Verne Organizations | PTM | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTM310 | Master Data Solution for Axway | PTM | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTM202 | Publish SNO plan as Master Schedule to ASCP - SNO | PTM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTM207 | IQS to EBS item inbound | PTM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTM240 | CR 207 LIMS OUTBOUND | PTM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTM252 | PQS to EBS Lot Status Inbound Interface Requirements | PTM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTM254 | PQS Item master inbound to EBS | PTM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTM261 | L3 Commissiong Interface | PTM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTM262 | L3 Get Serial Numbers (Antares) | PTM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTM271 | L3 Get Serial Numbers (Systech) | PTM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTM282 | BOM EBS --> KINAXIS | PTM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTM285 | Get Serial Number Requests/Reply for CMO | PTM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTM286 | Sourcing History Outbound | PTM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTM293 | Serial Number import Interface – Gilead Request numbers from Astellas and import it into Axway | PTM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTM298 | Master Data Import to Axway | PTM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTM311 | ISCP-Analytics | PTM | i |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTM316 | GIL External Serialization Event Capturing Interface | PTM | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTP126 | Extension in I proc to force a ship to location for Chemical delivery | PTP | E |  | Rewrite | Rewrite | INT1 | CD1.3 | FBD Completed | 2018-05-18 | Out of scope |  |  | #VALUE! | #VALUE! |  | 2018-08-04 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTP174 | SLM: OA Page Extensions | PTP | E |  | Rewrite | Rewrite | INT1 | CD1.3 | FBD Pending | 2018-07-06 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | WPTP135 | Customization to AP Invoice approval workflow to increase notification timeout to 45 days | PTP | W |  | Rewrite | Rewrite | INT1 | CD1.3 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | WPTP175 | SLM: Enhancement to POS: Supplier Approval Management | PTP | W |  | Rewrite | Rewrite | INT1 | CD1.3 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | WPTP176 | SLM: Enhancement to POS: Supplier Approval and profile management | PTP | W |  | Rewrite | Rewrite | INT1 | CD1.3 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | WPTP31 | PO approval workflow customization | PTP | W |  | Rewrite | Rewrite | INT1 | CD1.3 | FBD Completed | 2018-06-08 | Automation completed | [5 empty] | 2018-08-05 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | WRTR89 | Requisition Account Generator | PTP | W |  | Rewrite | Rewrite | INT1 | CD1.3 | FBD Completed | 2018-05-18 | Out of scope |  |  | #VALUE! | #VALUE! |  | 2018-08-05 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | WRTR90 | PO Account Generator | PTP | W |  | Rewrite | Rewrite | INT1 | CD1.3 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | WRTR91 | Payables Account Generator | PTP | W |  | Rewrite | Rewrite | INT1 | CD1.3 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | WPTP100 | PO Account Generator modification for PTP | PTP | W |  | Rewrite | Rewrite | INT1 | CD2.1 | FBD Completed | 2018-06-08 | Automation completed | [5 empty] | 2018-08-05 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | WPTP201 | OIMS: Collaboration Notification | PTP | E |  | Rewrite | Rewrite | INT2 | CD2.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | WPTP29 | Requisition Workflow customization | PTP | W |  | Rewrite | Rewrite | INT1 | CD2.1 | FBD Completed | 2018-05-18 | Out of scope |  |  | #VALUE! | #VALUE! |  | 2018-08-05 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTP127 | Invoice search form in EBS ( Adding elements in the seeded SLA search form) | PTP | E |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-05-11 | Out of scope | [5 empty] | 2018-06-26 | [6 empty] | Manual | 2018-06-26 | [6 empty] | Not Started
#REF! | EPTP186 | Payment Batch Approval | PTP | E |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed |  | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-06-26 | [6 empty] | Partial | 2018-06-26 | [6 empty] | Not Started | #VALUE!
#REF! | EPTP32 | Customization in Requisition form to allow specific user access | PTP | E |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-05-18 | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-06-26 | [6 empty] | Partial | 2018-06-26 | [6 empty] | Not Started
#REF! | IPTP83 | AP Expense Invoices Inbound(Concur) | PTP | I |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed |  | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-07-25 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTP125 | Input Tax Reconciliation by expense account Report | PTP | R |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-05-14 | Automation completed | [5 empty] | 2018-07-16 | [6 empty] | Partial | 2018-07-04 | [6 empty] | Not Started
#REF! | RPTP187 | Supplier Remittance Advice Report | PTP | R |  | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Automation completed | [5 empty] | 2018-07-16 | [6 empty] | Partial | 2018-06-26 | [6 empty] | Not Started
#REF! | EPTP172 | Automate EBS access through IDM automation | PTP | E |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTP192 | Business Conduct Dashboard (Commercial) | PTP | E |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | 2018-07-06 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTP199 | OIMS: Work Groups | PTP | E |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTP222 | OIMS header and lines WEBADI | PTP | E |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTP99 | Cheque Request - Custom Form, Integration with invoice interface table | PTP | E |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | 2018-07-13 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTP166 | GIL AGS360 Expenses Extract from EBS to ODS | PTP | I |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | IPTP214 | CAR to EBS PO Interface | PTP | I |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-06-08 | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-07-13 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTP124 | HCP Spend Analysis Report | PTP | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTP129 | EDD report for California contractors | PTP | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | 2018-07-20 | Out of scope | 7 |  |  | 7 |  | 2018-08-01 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | RPTP150 | GIL Aggregate Spend Physicians Clinical and R&D Extract | PTP | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTP151 | GIL Aggregate Spend Entities Clinical and R&D Extract | PTP | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTP152 | GIL Aggregate Spend Physicians GILDA Extract | PTP | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTP153 | GIL Aggregate Spend Entities GILDA Extract | PTP | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTP170 | Aggregate spend - Report for IPP source only | PTP | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTP190 | GIL Exhibits/Grants Extract | PTP | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | 2018-07-20 | Out of scope | 7 |  |  | 7 |  | 2018-08-01 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | RPTP191 | GIL Physicians Non-Research Extract | PTP | R |  | Retrofit | Retrofit | INT1 | CD1.2 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTP169 | Centraized AP and PO Close | PTP | E |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTP183 | EBS cross functional batch monitoring | PTP | E |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-06 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTP198 | OIMS: Invoice Search | PTP | E |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTP200 | OIMS: Invoice Listing, Processing and Sub Components | PTP | E |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTP23 | New form for audit schedules and capturing Corrective action plan details | PTP | E |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Completed | 2018-06-01 | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-08-04 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTP30 | Customization in Purchase Order form for special approvals/Notifications | PTP | E |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-13 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTP204 | OIMS: Invoice Inbound derivations, validations and processing | PTP | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-13 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IPTP205 | OIMS: Supplier Outbound to Transcepta | PTP | I |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-20 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTP216 | GIL AP Aging Report | PTP | R |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTP219 | GIL OIMS Department Invoice Status Report | PTP | R |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | WPTP202 | OIMS: Consolidated Notification | PTP | E |  | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTP128 | Invoice Data Dump From EBS to include Invoice Hold Types & Dates | PTP | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-15 | Automation completed | [5 empty] | 2018-07-10 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | EPTP141 | IPV and ERV | PTP | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-14 | Automation completed | [5 empty] | 2018-07-10 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | EPTP181 | Intercompany Invoice Clearing Account Correction | PTP | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-15 | Automation completed | [5 empty] | 2018-07-11 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | RPTP93 | PO Format / Customer Facing Document | PTP | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-30 | Automation completed | [5 empty] | 2018-07-17 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTP104 | Check Printing Program | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-08 | Out of scope | [5 empty] | 2018-07-03 | [6 empty] | Manual | 2018-07-03 | [6 empty] | Not Started
#REF! | EPTP107 | Extension for Document Sequencing in AP Invoice | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-14 | Automation completed | [5 empty] | 2018-07-05 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | EPTP122 | Extension to extract Clinical Trial Data for CompleteSpend system | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-15 | Automation completed | [5 empty] | 2018-07-05 | [6 empty] | Automation | [7 empty] | Not Started
#REF! | EPTP123 | Extension to email Greek MYF Output file to user | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-14 | Automation completed | [5 empty] | 2018-07-05 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTP138 | Project Wrap UP customization | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTP140 | Mandatory EH&S Approval automation | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTP142 | Add Dept Field to Payment Request | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTP145 | Make Note to Buyer Mandatory on Requisitions for adding Funds | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-18 | Automation completed |  |  | 2 | #VALUE! |  | 2018-07-06 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTP154 | Supplier extract to EDQ | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-17 | Automation completed | [5 empty] | 2018-07-05 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTP155 | Supplier Update Tool | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-01 | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-07-06 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTP156 | GIL mass close program | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTP168 | GIL Cancel unused/rejected GPRs | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTP173 | Resrict users from updating certain fields on AP invoice | PTP | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-06 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTP179 | CR1535 - Require receipts on iExpense | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-08 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTP180 | CR# 982 - Account Derivation for Freight and Misc charges | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-08 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTP184 | Iexpense OAF Customization | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-09 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTP193 | Aggegate spend - Currency rates extract | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-09 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTP194 | Custom Alert for AGIS | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-09 | [5 empty] | MD50, MD70 not avaialble | Manual | [7 empty] | Not Started
#REF! | EPTP195 | SWIFT Alliance Access | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-07-09 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTP20 | An Alert to show remaining amount on PO's crossing threshold value | PTP | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-06 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTP209 | OIMS: Invoice Attachment Extension | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTP211 | OIMS: OSN XML Gateway Extension | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTP212 | OIMS: Background Sweep Program | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTP215 | Alert for AGIS Transactions submitted without Recipient Accounting | PTP | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-13 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [5 empty] | MD50, MD70 not avaialble | Manual | [7 empty] | Not Started
#REF! | EPTP223 | OIMS Invoice Image Batch Printing | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-09 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTP224 | OIMS backport from EBS for Grants, IPP, GPR | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTP226 | Concurrent Request archival program | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-09 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | EPTP227 | OIMS Data Archival | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | EPTP39 | Customize desktop receipt page to limit desktop receiving | PTP | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed |  | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-07-09 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | EPTP51 | Attach remittance advice and notify AP to send it along with Payment(Customization in XML template) | PTP | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | [5 empty] | 2018-07-02 | [6 empty] | Partial | 2018-07-03 | [6 empty] | Not Started
#REF! | EPTP82 | AME scripts for invoice approval workflow - including cross charging | PTP | E |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-03 | Out of scope | 7 |  |  | 7 |  | 2018-08-09 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTP1/5 | Worker (Employee) interface from HRIS/Gnet | PTP | I |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed |  | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-07-20 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IPTP103 | Positive pay to Wells Fargo | PTP | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | [5 empty] | 2018-07-06 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTP162 | AP Invoice approval status from EBS to Zoommedia (CCF) | PTP | I |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-13 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IPTP163 | Inbound Interface of Pcard Transactions into iExpense | PTP | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | [5 empty] | 2018-07-06 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTP167 | GIL Concur attendees Data Loader from CONCUR to EBS | PTP | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-10 | Pending Automation Design | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTP185 | Outbound Payment Interface from EBS to SWIFT | PTP | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Pending Automation Design |  |  | #VALUE! | #VALUE! |  | 2018-07-20 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | IPTP208 | OIMS: Model-N Interface to OIMS | PTP | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-10 | Out of scope | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTP221 | GIL AP Invoice inbound from ACCUIMAGE | PTP | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-10 | Out of scope | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTP228 | GIL move concurrent program output file to GEM | PTP | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-10 | Out of scope | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTP229 | Outbound Interface for Spain SII AP invoice Tax Details. | PTP | I |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-10 | Out of scope | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | IPTP84/6 | Payments Outbound Interface(Concur,Model N,Gilda,Counsel Link) | PTP | I |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-20 | Out of scope | 7 |  |  | 7 |  | 2018-07-31 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | RPTP105 | Custom Accrual Report | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-10 | Out of scope | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | RPTP106 | Entitlement Summary Report | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTP108 | Trial Balance reports total by Foreign currency (Open Item revaluation report) | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-10 | Out of scope | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | RPTP109 | Supplier Master Change Tracking Report | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-01 | Automation completed | [5 empty] | 2018-07-16 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTP134 | Custom RNV accounting reconciliation Report | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-11 | Automation completed | [5 empty] | 2018-07-16 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTP136 | Detail Remittances Report | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | [5 empty] | 2018-07-16 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTP143 | AP custom trade report | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-10 | Out of scope | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | RPTP144 | Supplier master data with tax details report | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-01 | Automation completed | [5 empty] | 2018-07-16 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTP147 | GIL Aggregate Spend Exhibits Extract | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-10 | Out of scope | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | RPTP148 | GIL Aggregate Spend Grants Extract | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-10 | Out of scope | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | RPTP149 | GIL Aggregate Spend Physicians Commercial Extract | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTP158 | HCP Audit report | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-10 | Out of scope | 7 |  |  | 7 |  | 2018-08-13 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | RPTP159 | GIL New Supplier Report - Aggregate spend phase 1 | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTP164 | GIL Approved Suppliers Report | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-01 | Out of scope |  |  | 2 |  |  | 2018-07-13 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTP171 | Create one instuction to Oracle for payment batches | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Pending Automation Design |  |  | 6 |  |  | 2018-07-03 | [6 empty] | Partial | 2018-07-03 | [6 empty] | Not Started
#REF! | RPTP182 | Invoice hold report | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-15 | Automation completed | [5 empty] | 2018-07-16 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTP189 | Purchase Order Spend Analysis Reports - VMS Implementation | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTP196 | GIL Italian Purchase VAT Register report | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTP197 | AP Invoice aging report | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-11 | Automation completed | [5 empty] | 2018-07-17 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTP217 | GIL Accrual Report | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTP218 | GIL Invoice Intake Reconciliation Detail Report | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTP220 | GIL Invoice Intake Reconciliation Summary Report | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | #N/A | Pending Automation Design | #N/A | #N/A | #N/A | #N/A |  | #REF! | [6 empty] | Partial
#REF! | RPTP46 | Report showing duplicate invoices across Gilead entities | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-08-17 | Out of scope | 7 |  |  | 7 |  | 2018-08-17 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | RPTP52 | Custom Program to capture person who printed checks | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-05-15 | Automation completed | [5 empty] | 2018-07-17 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTP53 | Report to provide check printing audit trail | PTP | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Pending Automation Design |  |  | 2 |  |  | 2018-07-02 | [6 empty] | Partial | 2018-07-02 | [6 empty] | Not Started | #VALUE!
#REF! | RPTP54 | Create a prepayment register report that identifies risk based payments | PTP | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-08 | Automation completed | [5 empty] | 2018-07-17 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTP56 | 1099 exception listing report | PTP | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-12 | Automation completed | [5 empty] | 2018-07-17 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTP67 | P-Card reconcilliation report to idnentify processed and unprocessed transactions | PTP | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-15 | Automation completed | [5 empty] | 2018-07-17 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | RPTP92 | Report to show PO Receipts to Meximo | PTP | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-08 | Automation completed | [5 empty] | 2018-07-17 | [6 empty] | Partial | 2018-07-03 | [6 empty] | Not Started | #VALUE!
#REF! | EPTP230 | 12.2 Iproc UI personalizations and customizations | PTP | E |  | New | New | INT1 | CD1.3 | FBD Pending | 2018-07-13 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | RPTP231 | GIL OIMS Audit Report | PTP | R |  | New | New | INT2 | CD2.1 | FBD Pending | 2018-07-27 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | CPTP102 | Conversion of Bank and bank branch | PTP | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CPTP146 | GIL Aggregate Spend Project – For Sunshine Act | PTP | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CPTP188 | Western Union Supplier Bank Account conversion | PTP | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CPTP213 | OIMS: Supplier Update | PTP | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CPTP225 | Invoice conversion from BW to OIMS | PTP | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CPTP76 | Conversion of Suppliers | PTP | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CPTP77 | Conversion of Open AP Invoices | PTP | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CPTP78 | Conversion of Open Purchase Orders | PTP | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CPTP85 | Conversion of Receipts | PTP | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CPTP87 | Conversion of Employee | PTP | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTP111 | Brainware - Supplier View | PTP | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTP112 | Brainware - Function to validate COA combination against EBS | PTP | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTP115 | Brainware - Function to derive account code based on project | PTP | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTP117 | Brainware - PO Info View to BW | PTP | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTP118 | Brainware - View into EBS to check hold code status | PTP | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTP120 | Brainware - View of invoices in EBS for purpose of duplicate check | PTP | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTP130 | Exchange Rate data and Approval Matrix Data extract from EBS for Brainware. Two EBS extracts and 2 EBS Views for Brianware. | PTP | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTP139 | Brainware Aug 2012 Bundled Release | PTP | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTP157 | Supplier DFF update program | PTP | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTP160 | Load BIC and IBAN for bank accounts | PTP | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTP161 | PO Conversion from CO 6 and Co7 to Co1 | PTP | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTP165 | AP Create Accounting Fix | PTP | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTP177 | Japan: Automate BOA PAT ID communication via email | PTP | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTP203 | OIMS: Sync Invoice Date on Invoice WB to OIMS staging | PTP | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTP210 | OIMS: Manual Upload WebADI Extension | PTP | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | EPTP74 | Program to convert Invoice/Payment request data to image | PTP | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTP119 | Brainware - AP Invoices/Payment request Inbound interface from BW to EBS | PTP | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTP137 | Automate hierarchy file transfer to TRX site | PTP | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTP14 | Interface for PCards transactions from US Bank | PTP | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTP18 | Brainware - Gilda/Model N/Council Link to BW | PTP | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTP206 | OIMS: PO Outbound to Transcepta | PTP | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTP207 | OIMS: Payment Feed Outbound to Transcepta | PTP | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTP89 | Interface from EBS to Ruesch for payments | PTP | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTP90 | Interface from Ruesch to EBS with payments confirmation including FX | PTP | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | IPTP91 | Interface from EBS to BOA for payments | PTP | I |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | RPTP178 | Japan: BOA PAT ID Report | PTP | R |  | Decommissioned | Decommissioned | N/A | N/A | FBD Completed | 2018-05-14 | Automation completed | [5 empty] | 2018-08-04 | [6 empty] | Partial | [7 empty] | Not Started
#REF! | WPTP38 | Proactive Notification to perform desktop receipt | PTP | W |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | WRTR57 | Customized Journal Approval Workflow | RTR | W | P4 | Rewrite | Rewrite | INT1 | CD1.3 | FBD Pending | 2018-07-13 | Pending Automation Design | 7 |  | 6 | 1 | Design | #REF! |  |  | 2018-08-01 | 2018-08-02 | Raja |  | Partial | [7 empty] | Not Started
#REF! | ERTR103 | A new object needs to be created to interface the cost related to R&D Depreciation, International Payroll, GL allocation and Benefits to OPC in Gen Admin projects from General Ledger. | RTR | E | P1 | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed |  |  |  |  | Execution | 2018-06-26 | 2018-07-06 | 2018-07-16 | 2018-07-17 | 2018-07-19 | Nilam | GEM Team to run the services which load data in the EBS stagging tables (IRTR105 need to pass) | Automation | 2018-06-26 | 2 |  |  |  | 19 |  | Pending
#REF! | RRTR56 | Report to show intercompany AR AP transaction information | RTR | R | P1 | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-07-27 | Automation completed |  |  | 9 | #VALUE! |  | 2018-07-13 | 2018-07-16 | 2018-07-16 | 2018-07-17 | 2018-07-18 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | EMGR22 | Custom form for cross charge hierarchy | RTR | E | P1 | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-06 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [5 empty] | MD50, MD70 not avaialble | Partial | [7 empty] | Not Started
#REF! | EMGR28 | EBS Outbound to Hyperion - Trial Balance, Project Cost, Fixed Assets All, and Item Cost and OPM Routing | RTR | E | P1 | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-06 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | [5 empty] | MD50, MD70 not avaialble | Partial | [7 empty] | Not Started
#REF! | IRTR118 | Import GL Journals Inbound interface - ADP Journal entries | RTR | I | P1 | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-06 | Pending Automation Design | 8 |  | 6 | 2 |  | #REF! | 2018-07-16 | 2018-07-24 | 2018-07-25 | 2018-07-27 | Nilam | Dependancy on GEM Team | Partial | [7 empty] | Not Started
#REF! | IRTR5 | GL Journals Outbound Interface (AssureNet) | RTR | I | P1 | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-06 | Pending Automation Design | 7 |  | 6 | 1 |  | #REF! | 2018-07-16 | 2018-07-24 | 2018-07-27 | 2018-08-01 | Nilam | Dependancy on GEM Team | Partial | [7 empty] | Not Started
#REF! | RRTR102 | RTR Change Request for RRTR87 - Period Parameters. | RTR | R | P1 | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-06 | Pending Automation Design | 11 |  | 9 | 2 |  | #REF! | 2018-07-30 | 2018-07-31 | 2018-08-01 | 2018-08-02 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | RRTR15/16 | Report to show difference between US and local GAAP | RTR | R | P1 | Retrofit | Retrofit | INT1 | CD1.3 | FBD Completed | 2018-06-13 | Pending Automation Design |  |  | 23 |  |  | 2018-08-04 | 2018-07-30 | 2018-07-31 | 2018-08-03 | 2018-08-07 | Nilam |  | Automation | [7 empty] | Not Started
#REF! | RRTR45 | Report to show trace allocations in the system | RTR | R | P1 | Retrofit | Retrofit | INT1 | CD1.3 | FBD Completed | 2018-07-27 | Automation completed |  |  | 11 | #VALUE! |  | 2018-08-04 | 2018-07-30 | 2018-07-31 | 2018-08-08 | 2018-08-09 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | RRTR105 | Customize Transactions available for Reconciliation Report | RTR | R | P3 | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 5 |  |  |  |  | 2018-07-17 | 2018-07-13 | 2018-07-13 | 2018-07-16 | 2018-07-17 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | RRTR112 | New GIL Retired Assets Depreciation Report | RTR | R | P3 | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 14 | 12 |  | 2 | Execution | [5 empty] | Nilam |  | Partial | 2018-07-12 | 14 | [5 empty] | Pending
#REF! | RRTR48 | Report to show original system asset numbers from a DFF | RTR | R | P3 | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 7 |  |  |  | Execution | [5 empty] | Nilam |  | Partial | 2018-07-11 | 7 | 2 |  |  |  |  | Pending
#REF! | RRTR55 | "Fixed Asset All" report | RTR | R | P3 | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 8 |  |  |  |  | 2018-07-18 | 2018-07-16 | 2018-07-16 | 2018-07-17 | 2018-07-19 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | ERTR114 | Elimination set automation | RTR | E |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-06 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [5 empty] | MD50, MD70 not avaialble | Manual | [7 empty] | Not Started
#REF! | ERTR117 | Automation of Secondary Ledger accounting for fixed assets | RTR | E | P2 | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-07-06 | Out of scope | 11 |  |  | 11 | Execution | 2018-08-02 | 2018-08-03 | 2018-08-03 | 2018-08-06 | 2018-08-07 | Nilam |  | Manual | [7 empty] | Not Started
#REF! | ERTR122 | AGIS Transaction upload WEBADI | RTR | E | P2 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Pending Automation Design | 6 |  | 5 | 1 | Execution | 2018-07-09 | 2018-08-06 | 2018-08-06 | 2018-08-07 | 2018-08-10 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | IRTR1 | Bank Statements & Re-counc. Inbound interface(B2B) | RTR | I | P2 | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-15 | Pending Automation Design | 12 |  | 10 | 2 | Execution | 2018-07-20 | 2018-07-16 | 2018-07-24 | 2018-07-16 | 2018-07-20 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | IRTR2 | Import GL Journals Inbound interface - HR Headcount | RTR | I | P2 | Retrofit | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-06 | Out of scope | 10 |  |  | 10 |  | 2018-08-01 | [5 empty] | Pending clarification from Sree/Satish | Manual | [7 empty] | Not Started
#REF! | IRTR3 | Chart of Accounts Outbound interface | RTR | I | P2 | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-13 | Out of scope | 1 |  |  | 1 |  | 2018-08-01 | [5 empty] | Pending clarification from Sree/Satish | Manual | [7 empty] | Not Started
#REF! | RRTR101 | GL Interface unprocessed transactions Report | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | 8 |  |  |  |  | 2018-07-17 | 2018-07-18 | 2018-07-18 | 2018-07-19 | 2018-07-20 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | RRTR108 | Secondary ledger detailed transaction report | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | 6 |  |  |  |  | 2018-07-17 | 2018-07-20 | 2018-07-20 | 2018-07-23 | 2018-07-24 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | RRTR109 | Italian 'Libro Giornale' report template changes | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 6 |  |  |  |  | 2018-07-17 | 2018-07-23 | 2018-07-23 | 2018-07-24 | 2018-07-26 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | RRTR115 | Turkey eLedger | RTR | R |  | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-13 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [5 empty] | MD50, MD70 not avaialble | Manual | [7 empty] | Not Started
#REF! | RRTR121 | Customized Account Analysis Report | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | 5 |  |  |  |  | 2018-07-16 | 2018-07-25 | 2018-07-25 | 2018-07-26 | 2018-07-30 | Nilam |  | Automation | [7 empty] | Not Started
#REF! | RRTR17 | Custom EBS Report for Journal WHO information | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 14 |  |  |  |  | 2018-07-16 | 2018-07-27 | 2018-07-27 | 2018-07-30 | 2018-08-02 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | RRTR30 | Custom report for non-capitalized asset listings | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 8 |  |  |  | Execution | [5 empty] | Sulagna | Inputs waiting from Satish | Partial | 2018-06-26 |  |  |  |  | 1 |  | Pending | #VALUE!
#REF! | RRTR31 | Reconciliation report on the difference between US and local GAAP | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | 8 |  |  |  |  | 2018-07-17 | 2018-08-10 | 2018-08-10 | 2018-08-11 | 2018-08-12 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | RRTR47 | Report to classify assets as new or replacement cost | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 8 |  |  |  |  | 2018-07-18 | 2018-08-10 | 2018-08-10 | 2018-08-13 | 2018-08-13 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | RRTR49 | "What-if" Depreciation/Amortization Reports | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 20 |  |  |  |  | 2018-07-18 | 2018-08-07 | 2018-08-07 | 2018-08-08 | 2018-08-16 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | RRTR50 | Report on Audit Trail of changes on asset status | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 6 |  |  |  |  | 2018-07-18 | 2018-08-15 | 2018-08-15 | 2018-08-16 | 2018-08-16 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | RRTR69 | Report on process exceptions | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | 26 |  |  |  | Execution | 2018-07-18 |  |  |  |  | Nilam |  | Partial | 2018-07-03 | 11 | 15 |  |  |  |  | Pending
#REF! | RRTR86 | Fixed Asset Listing with Statutory Codes – Fixed Asset Report | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-15 | Out of scope | 4 |  | 14 |  |  | 2018-07-18 |  |  | 2018-08-02 | 2018-08-04 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | RRTR87 | Fixed Asset Quarterly Rollforward for SEC – Fixed Asset Report | RTR | R |  | Retrofit | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-13 | Out of scope | 7 |  |  | 7 |  | 2018-08-02 | [5 empty] | MD50, MD70 not avaialble | Manual | [7 empty] | Not Started
#REF! | RRTR94 | Primary to Secondary COA Mapping Exceptions Report | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | 6 |  |  |  |  | 2018-07-18 | 2018-07-19 | 2018-07-19 | 2018-07-20 | 2018-07-24 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | ERTR104 | Prevent project cost from being posted to unspecified depts | RTR | E | P3 | Retrofit | No code change required | INT1 | CD1.2 | FBD Completed | 2018-06-13 | Automation completed | 5 |  | 1 | 4 | Execution | 2018-07-19 | 2018-08-09 | 2018-08-10 | 2018-08-13 | 2018-08-15 | Nilam |  | Partial | [7 empty] | Not Started
#REF! | RRTR113 | Project Receiving Status Report | RTR | R |  | Retrofit | Decommissioned | INT1 | CD1.2 | FBD Pending | 2018-07-06 | Out of scope | 12 |  |  | 12 |  | 2018-08-02 | [6 empty] | Manual | [7 empty] | Not Started
#REF! | CRTR75 | Conversion of COA | RTR | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CRTR76 | Conversion of GL Balances | RTR | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | CRTR77 | Conversion of Fixed Assets | RTR | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
#REF! | ERTR105 |  | RTR | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned | [20 empty] | Not Started
| WRTR57 | Customized Journal Approval Workflow | RTR | W | P4 | Rewrite | Rewrite | INT1 | CD1.3 | FEB Pending | 2018-07-13 | Pending Automation Design | 7 |  |  | 7 | Execution |  | 2018-08-12 | 2018-08-12 | 2018-08-13 | 2018-08-14 | Nilam | [9 empty] | Not Started
Formulas:
Design = VLOOKUP([WICER Object Details],'[2]Data from Pivot'!$F4:G224,2,FALSE)
Execution = [Design]+3
Execution = [Actual Test Execution date]

## RICEW Tracker
WICER Object Details | [9 empty] | Design | [6 empty] | Execution
RICEW ID | Description | Work Stream | Object Type | Priority | New/Retrofit/No code change required | New/Retrofit/No code change required - Revised | Test Cycle | Gilead Code Drop Bucket | FBD Completed (Yes/No) | FBD Completion date | Automation design completion (Y/N/Out of scope/Decommissioned) | Total Test Cases Planned | Full Automated TC Count | Partial Automation TC Count | Full manual TC Count | Design / Execution | Planned Execution date | Pre requisites start date mm/dd/yyyy | Pre Requisite end date mm/dd/yyyy | Revised Planned Start Date mm/dd/yyyy | Revised Planned End Date mm/dd/yyyy | Resource Name | Dependency | Manual/ Automation | Actual Test Execution date | Passed | Failed | Blocked | Not Completed | No Run | Defect id | Status | Execution In progress%
ERTR103 | A new object needs to be created to interface the cost related to R&D Depreciation, International Payroll, GL allocation and Benefits to OPC in Gen Admin projects from General Ledger. | RTR | E | P1 | Retrofit | Retrofit | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 21 |  |  |  | Execution | 2018-06-26 | 2018-07-06 | 2018-07-16 | 2018-07-17 | 2018-07-19 | Nilam | GEM Team to run the services which load data in the EBS stagging tables (IRTR105 need to pass) | Automation | 2018-06-26 | 2 |  |  |  | 19 |  | Pending
RRTR56 | Report to show intercompany AR AP transaction information | RTR | R | P1 | Retrofit | Retrofit | INT1 | CD1.2 | FBD Completed | 2018-07-27 | Automation completed |  |  | 9 | #VALUE! | Execution | 2018-07-13 | 2018-07-16 | 2018-07-16 | 2018-07-17 | 2018-07-18 | Nilam |  | Partial | [7 empty] | Not Started
EMGR22 | Custom form for cross charge hierarchy | RTR | E | P1 | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-06 | Pending Automation Design | 7 |  | 6 | 1 | Execution | #REF! | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 |  | MD50, MD70 not avaialble | Partial | [7 empty] | Not Started
EMGR28 | EBS Outbound to Hyperion - Trial Balance, Project Cost, Fixed Assets All, and Item Cost and OPM Routing | RTR | E | P1 | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-06 | Pending Automation Design | 7 |  | 6 | 1 | Execution | #REF! | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 |  | MD50, MD70 not avaialble | Partial | [7 empty] | Not Started
IRTR118 | Import GL Journals Inbound interface - ADP Journal entries | RTR | I | P1 | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-06 | Pending Automation Design | 8 |  | 6 | 2 | Execution | #REF! | 2018-07-16 | 2018-07-24 | 2018-07-25 | 2018-07-26 | Nilam | Dependancy on GEM Team | Partial | [7 empty] | Not Started
IRTR5 | GL Journals Outbound Interface (AssureNet) | RTR | I | P1 | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-06 | Pending Automation Design | 7 |  | 6 | 1 | Execution | #REF! | 2018-07-16 | 2018-07-24 | 2018-07-27 | 2018-07-30 | Nilam | Dependancy on GEM Team | Partial | [7 empty] | Not Started
RRTR102 | RTR Change Request for RRTR87 - Period Parameters. | RTR | R | P1 | Retrofit | Retrofit | INT1 | CD1.3 | FBD Pending | 2018-07-06 | Pending Automation Design | 11 |  | 9 | 2 | Execution | #REF! | 2018-07-29 | 2018-07-31 | 2018-07-31 | 2018-08-02 | Nilam |  | Partial | [7 empty] | Not Started
RRTR15/16 | Report to show difference between US and local GAAP | RTR | R | P1 | Retrofit | Retrofit | INT1 | CD1.3 | FBD Completed | 2018-06-13 | Pending Automation Design |  |  | 23 |  | Execution | 2018-08-04 | 2018-07-29 | 2018-07-31 | 2018-08-03 | 2018-08-09 | Nilam |  | Automation | [7 empty] | Not Started
RRTR45 | Report to show trace allocations in the system | RTR | R | P1 | Retrofit | Retrofit | INT1 | CD1.3 | FBD Completed | 2018-07-27 | Automation completed |  |  | 11 | #VALUE! | Execution | 2018-08-04 | 2018-07-29 | 2018-07-31 | 2018-08-08 | 2018-08-09 | Nilam |  | Partial | [7 empty] | Not Started
RRTR105 | Customize Transactions available for Reconciliation Report | RTR | R | P3 | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 5 |  |  |  | Execution | 2018-07-17 | 2018-07-13 | 2018-07-13 | 2018-07-16 | 2018-07-17 | Nilam |  | Partial | [7 empty] | Not Started
RRTR112 | New GIL Retired Assets Depreciation Report | RTR | R | P3 | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 14 | 12 |  | 2 | Execution |  | 2018-07-11 | 2018-07-12 | 2018-07-11 | 2018-07-12 | Nilam |  | Partial | 2018-07-12 | 14 | [5 empty] | Completed
RRTR48 | Report to show original system asset numbers from a DFF | RTR | R | P3 | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 7 |  |  |  | Execution |  | 2018-06-27 | 2018-06-28 | 2018-06-27 | 2018-06-28 | Nilam |  | Partial | 2018-07-11 | 7 | 2 |  |  |  |  | Completed
RRTR55 | "Fixed Asset All" report | RTR | R | P3 | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 8 |  |  |  | Execution | 2018-07-18 | 2018-07-16 | 2018-07-16 | 2018-07-17 | 2018-07-19 | Nilam |  | Partial | [7 empty] | Not Started
ERTR114 | Elimination set automation | RTR | E | P1 | Retrofit | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-06 | Out of scope | 7 |  |  | 7 | Execution | 2018-08-02 | 2018-08-10 | 2018-08-10 | 2018-08-10 | 2018-08-10 | Nilam | MD50, MD70 not avaialble | Manual | [7 empty] | Not Started
ERTR117 | Automation of Secondary Ledger accounting for fixed assets | RTR | E | P2 | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-07-06 | Out of scope | 11 |  |  | 11 | Execution | 2018-08-02 | 2018-08-03 | 2018-08-03 | 2018-08-06 | 2018-08-09 | Nilam |  | Manual | [7 empty] | Not Started
ERTR122 | AGIS Transaction upload WEBADI | RTR | E | P2 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Pending Automation Design | 6 |  | 5 | 1 | Execution | 2018-07-09 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-10 | Nilam |  | Partial | [7 empty] | Not Started
IRTR1 | Bank Statements & Re-counc. Inbound interface(B2B) | RTR | I | P2 | Retrofit | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-15 | Pending Automation Design | 12 |  | 10 | 2 | Execution | 2018-07-20 | 2018-07-16 | 2018-07-24 | 2018-07-16 | 2018-07-20 | Nilam |  | Partial | [7 empty] | Not Started
IRTR2 | Import GL Journals Inbound interface - HR Headcount | RTR | I | P2 | Retrofit | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-06 | Out of scope | 10 |  |  | 10 | Execution | 2018-08-01 | 2018-08-25 | 2018-08-25 | 2018-08-09 | 2018-08-09 | Nilam | Pending clarification from Sree/Satish | Manual | [7 empty] | Not Started
IRTR3 | Chart of Accounts Outbound interface | RTR | I | P2 | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-13 | Out of scope | 1 |  |  | 1 | Execution | 2018-08-01 | 2018-08-25 | 2018-08-25 | 2018-08-09 | 2018-08-09 | Nilam | Pending clarification from Sree/Satish | Manual | [7 empty] | Not Started
RRTR101 | GL Interface unprocessed transactions Report | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | 8 |  |  |  | Execution | 2018-07-17 | 2018-07-18 | 2018-07-18 | 2018-07-19 | 2018-07-20 | Nilam |  | Partial | [7 empty] | Not Started
RRTR108 | Secondary ledger detailed transaction report | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | 6 |  |  |  | Execution | 2018-07-17 | 2018-07-20 | 2018-07-20 | 2018-07-23 | 2018-07-24 | Nilam |  | Partial | [7 empty] | Not Started
RRTR109 | Italian 'Libro Giornale' report template changes | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 6 |  |  |  | Execution | 2018-07-17 | 2018-07-23 | 2018-07-23 | 2018-07-24 | 2018-07-25 | Nilam |  | Partial | [7 empty] | Not Started
RRTR115 | Turkey eLedger | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-13 | Out of scope | 7 |  |  | 7 | Execution | 2018-08-02 | 2018-08-10 | 2018-08-10 | 2018-08-10 | 2018-08-10 | Nilam | MD50, MD70 not avaialble | Manual | [7 empty] | Not Started
RRTR121 | Customized Account Analysis Report | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | 5 |  |  |  | Execution | 2018-07-16 | 2018-07-25 | 2018-07-25 | 2018-07-26 | 2018-07-27 | Nilam |  | Automation | [7 empty] | Not Started
RRTR17 | Custom EBS Report for Journal WHO information | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 14 |  |  |  | Execution | 2018-07-16 | 2018-07-27 | 2018-07-27 | 2018-07-30 | 2018-08-02 | Nilam |  | Partial | [7 empty] | Not Started
RRTR30 | Custom report for non-capitalized asset listings | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 8 |  |  |  | Execution |  | 2018-06-26 | 2018-06-27 | 2018-06-26 | 2018-06-27 | Sulagna | Inputs waiting from Satish | Partial | 2018-06-26 |  |  |  |  | 1 |  | Completed | #VALUE!
RRTR31 | Reconciliation report on the difference between US and local GAAP | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | 8 |  |  |  | Execution | 2018-07-17 | 2018-08-10 | 2018-08-10 | 2018-08-11 | 2018-08-13 | Nilam |  | Partial | [7 empty] | Not Started
RRTR47 | Report to classify assets as new or replacement cost | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 8 |  |  |  | Execution | 2018-07-18 | 2018-08-10 | 2018-08-10 | 2018-08-13 | 2018-08-13 | Nilam |  | Partial | [7 empty] | Not Started
RRTR49 | "What-if" Depreciation/Amortization Reports | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 20 |  |  |  | Execution | 2018-07-18 | 2018-08-07 | 2018-08-07 | 2018-08-08 | 2018-08-16 | Nilam |  | Partial | [7 empty] | Not Started
RRTR50 | Report on Audit Trail of changes on asset status | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-13 | Automation completed | 6 |  |  |  | Execution | 2018-07-18 | 2018-08-13 | 2018-08-13 | 2018-08-16 | 2018-08-16 | Nilam |  | Partial | [7 empty] | Not Started
RRTR69 | Report on process exceptions | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | 26 |  |  |  | Execution | 2018-07-18 | 2018-06-25 | 2018-06-28 | 2018-06-25 | 2018-06-28 | Nilam |  | Partial | 2018-07-03 | 11 | 15 |  |  |  |  | Completed
RRTR86 | Fixed Asset Listing with Statutory Codes – Fixed Asset Report | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed | 2018-06-15 | Out of scope | 4 |  | 14 |  | Execution | 2018-07-18 | 2018-07-29 | 2018-07-29 | 2018-08-02 | 2018-08-03 | Nilam |  | Partial | [7 empty] | Not Started
RRTR87 | Fixed Asset Quarterly Rollforward for SEC – Fixed Asset Report | RTR | R | P3 | Retrofit | No code change required | INT1 | CD1.1 | FBD Pending | 2018-07-13 | Out of scope | 7 |  |  | 7 | Execution | 2018-08-02 | 2018-08-10 | 2018-08-13 | 2018-08-13 | 2018-08-14 | Nilam | MD50, MD70 not avaialble | Manual | [7 empty] | Not Started
RRTR94 | Primary to Secondary COA Mapping Exceptions Report | RTR | R | P3 | No code change required | No code change required | INT1 | CD1.1 | FBD Completed |  | Automation completed | 6 |  |  |  | Execution | 2018-07-18 | 2018-07-19 | 2018-07-19 | 2018-07-20 | 2018-07-23 | Nilam |  | Partial | [7 empty] | Not Started
ERTR104 | Prevent project cost from being posted to unspecified depts | RTR | E | P3 | Retrofit | No code change required | INT1 | CD1.2 | FBD Completed | 2018-06-13 | Automation completed | 5 |  | 1 | 4 | Execution | 2018-07-19 | 2018-08-09 | 2018-08-10 | 2018-08-13 | 2018-08-17 | Nilam |  | Partial | [7 empty] | Not Started
RRTR113 | Project Receiving Status Report | RTR | R |  | Retrofit | Decommissioned | INT1 | CD1.2 | FBD Pending | 2018-07-06 | Out of scope | 12 |  |  | 12 | Execution | 2018-08-02 | [6 empty] | Manual | [7 empty] | Not Started
CRTR75 | Conversion of COA | RTR | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned |  |  |  |  | Execution | [15 empty] | Not Started
CRTR76 | Conversion of GL Balances | RTR | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned |  |  |  |  | Execution | [15 empty] | Not Started
CRTR77 | Conversion of Fixed Assets | RTR | C |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned |  |  |  |  | Execution | [15 empty] | Not Started
ERTR105 |  | RTR | E |  | Decommissioned | Decommissioned | N/A | N/A | Decommissioned |  | Decommissioned |  |  |  |  | Execution | [15 empty] | Not Started
WRTR57 | Customized Journal Approval Workflow | RTR | W | P1 | Rewrite | Rewrite | INT1 | CD1.3 | FEB Pending | 2018-07-13 | Pending Automation Design | 7 |  |  | 7 | Execution |  | 2018-08-10 | 2018-08-13 | 2018-08-13 | 2018-08-14 | Nilam | [9 empty] | Not Started
Formulas:
Design = VLOOKUP([WICER Object Details],'[2]Data from Pivot'!$F4:G224,2,FALSE)

## RTR Plan
PTM per Devesh plan |  |  |  | Summary
|  |  |  | 2018-07-13 | 2018-07-20 | 2018-07-27 | 2018-08-03 | 2018-08-10 | 2018-08-17 | 2018-08-24
Design |  |  |  | 19 | 18 | 12 | 10 | 7 |  |  |  | 66
Test Case Design |  |  |  |  | 104.5 | 99 | 66 | 55 | 38.5 |  |  | 363
Dependency
Execution |  |  |  | WICER | 10 | 13 | 14 | 26 | 28 | 47 |  | 138
|  |  |  | TC | 55 | 71.5 | 77 | 143 | 154 | 258.5 |  | 759
Automation |  |  |  |  | 16.5 | 21.45 | 23.1 | 42.9 | 46.2 | 77.55
Manual Res# |  |  |  | 2 | 38.5 | 50.05 | 53.9 | 100.1 | 107.8 | 180.95
per person per day |  |  |  |  | 3.85 | 5.005 | 5.39 | 10.01 | 10.78 | 18.095
Automation = 30%
Number of TC's per WICER |  |  |  | 5.5
Constrained |  |  |  | 2.5 | 3.08 | 4.004 | 4.312 | 8.008 | 8.624 | 14.476
Input
RTR Track |  |  | PTM Track Plan | [9 empty] | OTC Track Plan | [8 empty] | PRJ Track`
[32 empty] | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 2018-07-21 | 2018-07-22 | 2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-07-26 | 2018-07-27 | 2018-07-28 | 2018-07-29 | 2018-07-30 | 2018-07-31 | 2018-08-01 | 2018-08-02 | 2018-08-03 | 2018-08-04 | 2018-08-05 | 2018-08-06 | 2018-08-07 | 2018-08-08 | 2018-08-09 | 2018-08-10 | 2018-08-11 | 2018-08-12 | 2018-08-13 | 2018-08-14 | 2018-08-15 | 2018-08-16 | 2018-08-17
| Total WICERS | Total executed | Inputs | 2018-07-13 | 2018-07-20 | 2018-07-27 | 2018-08-03 | 2018-08-10 | 2018-08-17 | 2018-08-24 | 2018-08-31 |  | Inputs | 2018-07-13 | 2018-07-20 | 2018-07-27 | 2018-08-03 | 2018-08-10 | 2018-08-17 | 2018-08-24 | 2018-08-31 | Inputs | 2018-07-13 | 2018-07-20 | 2018-07-27 | 2018-08-03 | 2018-08-10 | 2018-08-17 | 2018-08-24 | 2018-08-31 | Inputs | 17-Jul | 18-Jul | 19-Jul | 20-Jul |  |  | 23-Jul | 24-Jul | 25-Jul | 26-Jul | 27-Jul |  |  | 30-Jul | 2018-07-31 | 2018-08-01 | 2-Aug | 3-Aug |  |  | 6-Aug | 2018-08-07 | 2018-08-08 | 9-Aug | 10-Aug |  |  | 13-Aug | 14-Aug | 2018-08-15 | 16-Aug | 17-Aug
CD1.1- WICER Count |  |  |  | 19 | 18 | 12 | 10 | 7 | [23 empty] | 2 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 2 | 2 | 1 | 0 | 2 | 0 | 0 | 1 | 0 | 21
Automation | bar: 2018-07-17; 2018-07-26
Manual | [31 empty] | 2018-08-06: 1; 2018-08-09: 2; 2018-08-10: 2; 2018-08-13: 1
Partial | bar: 2018-07-17 to 2018-07-20; 2018-07-23 to 2018-07-24; 2018-07-30; 2018-08-02; 2018-08-06; 2018-08-08; 2018-08-11; 2018-08-13; 2018-08-16
CD1.2-WICER Count | [31 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2
Automation
Manual
Partial | bar: 2018-07-17; 2018-08-13
CD1.3WICER Count | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8
Automation | bar: 2018-08-03
Manual
Partial | [31 empty] | 2018-07-25: 1; 2018-07-27: 1; 2018-07-31: 1; 2018-08-06: 2; 2018-08-08: 1; 2018-08-13: 1
(blank)
WICERS - Design
Test case design count |  |  |  |  | 104.5 | 99 | 66 | 55 | 38.5
Dependency = Test Data Creation in hrs |  |  |  | 36 | 46.8 | 54 | 82.8 | 90 | 90 | 97.2 | 0 |  |  | 28.8 | 108 | 115.2 | 115.2 | 72 | 72 | 0 | 0 |  | 28.8 | 108 | 115.2 | 115.2 | 72 | 72 | 0 | 0 |  | 2018-07-17: 0; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 0
Execution - WICER# | 155 |  |  |  | 10 | 13 | 15 | 23 | 25 | 25 | 27 |  |  |  | 4 | 15 | 16 | 16 | 10 | 10 |  |  |  | 4 | 15 | 16 | 16 | 10 | 10 |  |  | 3 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 4 | 0 | 2 | 2 | 2 | 1 | 0 | 4 | 0 | 0 | 1 | 0 | 31
Execution - TC # ( Including defect retest of 20%)-M |  |  |  |  | 72 | 93.6 | 108 | 165.6 | 180 | 180 | 194.4 |  |  |  | 28.8 | 108 | 115.2 | 115.2 | 72 | 72 |  |  |  | 28.8 | 108 | 115.2 | 115.2 | 72 | 72 |  |  | 2018-07-17: 0; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 0; 2018-07-27: 0; 2018-07-30: 0; 2018-08-02: 0; 2018-08-03: 0; 2018-08-06: 7.2; 2018-08-09: 14.4; 2018-08-10: 14.4; 2018-08-13: 7.2; 2018-08-14: 0; 2018-08-16: 0; 2018-08-17: 0 | 43.2
Execution - TC # ( Including defect retest of 20%)-A |  |  | 32% |  | 23.04 | 29.952 | 34.56 | 52.992 | 57.6 | 57.6 | 62.208 |  | 63% |  | 18.144 | 34.56 | 36.864 | 36.864 | 23.04 | 23.04 |  | 65% |  | 9.216 | 34.56 | 36.864 | 36.864 | 23.04 | 23.04 |  |  | 2018-07-17: 7.2; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 7.2; 2018-07-27: 0; 2018-07-30: 0; 2018-08-02: 0; 2018-08-03: 7.2; 2018-08-06: 0; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 0; 2018-08-14: 0; 2018-08-16: 0; 2018-08-17: 0 | 21.6
Execution - TC # ( Including defect retest of 20%)-P |  |  | 68% | 2 | 48.96 | 63.648 | 73.44 | 112.608 | 122.4 | 122.4 | 132.192 |  | 37% |  | 10.656 | 73.44 | 78.336 | 78.336 | 48.96 | 48.96 |  | 35% |  | 19.584 | 73.44 | 78.336 | 78.336 | 48.96 | 48.96 |  |  | 2018-07-17: 14.4; 2018-07-18: 7.2; 2018-07-19: 7.2; 2018-07-20: 7.2; 2018-07-23: 7.2; 2018-07-24: 7.2; 2018-07-25: 7.2; 2018-07-26: 0; 2018-07-27: 7.2; 2018-07-30: 7.2; 2018-08-02: 7.2; 2018-08-03: 0; 2018-08-06: 21.6; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 21.6; 2018-08-14: 0; 2018-08-16: 7.2; 2018-08-17: 0 | 129.6
Unconstrained per person per day |  |  |  |  | 4.896 | 6.3648 | 7.344 | 11.2608 | 12.24 | 12.24 | 13.2192 |  |  |  | 1.0656 | 7.344 | 7.8336 | 7.8336 | 4.896 | 4.896 |  |  |  | 1.9584 | 7.344 | 7.8336 | 7.8336 | 4.896 | 4.896 |  |  | 2018-07-18: 0.72; 2018-07-19: 0.72; 2018-07-20: 0.72; 2018-07-23: 0.72; 2018-07-24: 0.72; 2018-07-25: 0.72; 2018-07-26: 0; 2018-07-27: 0.72; 2018-07-30: 0.72; 2018-08-02: 0.72; 2018-08-03: 0; 2018-08-06: 2.16; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 2.16; 2018-08-14: 0; 2018-08-16: 0.72; 2018-08-17: 0
Total TCs | [31 empty] | 21.6 | 7.2 | 7.2 | 7.2 | 0 | 0 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 0 | 0 | 7.2 | 0 | 0 | 7.2 | 7.2 | 0 | 0 | 28.8 | 0 | 0 | 14.4 | 14.4 | 0 | 0 | 28.8 | 0 | 0 | 7.2 | 0 | 194.4
[32 empty] | update actual TCs(row 40,41,42) from tracker if Or level set the TCs for the day. This is crowded. | [19 empty] | update actual TCs(row 40,41,42) from tracker if Or level set the TCs for the day. This is crowded. | [6 empty] | update actual TCs(row 40,41,42) from tracker if Or level set the TCs for the day. This is crowded.
Hours per test case for verification for Partial test cases |  |  | 2 | [9 empty] | 2 | [8 empty] | 2 | [8 empty] | 2
Partial Automation verification hours/week |  |  | 32% | 2 | 37 | 48 | 55 | 85 | 92 | 92 | 100 |  | 63% | 2 | [7 empty] | 65% | 2 | [8 empty] | 2018-07-17: 23.04; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 11.52; 2018-07-27: 0; 2018-07-30: 0; 2018-08-02: 0; 2018-08-03: 11.52; 2018-08-06: 0; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 0; 2018-08-14: 0; 2018-08-16: 0; 2018-08-17: 0
2
Number of TC's per WICER |  |  | 6 | [9 empty] | 6 |  | 29 | 55 | 59 | 59 | 37 | 37 | 0 | 6 |  | 14.7456 | 55.296 | 58.9824 | 58.9824 | 36.864 | 36.864 |  | 6
Productivity test Execution (TC's / Day / person)-M |  |  | 2 | [9 empty] | 2 | [8 empty] | 3 | [8 empty] | 4
Productivity test Execution (TC's / Day / person)-A | [30 empty] | 15
Productivity test Execution (TC's / Day / person)-P | [30 empty] | 4
Execution - Effort - M TCs in hours | [31 empty] | 2018-07-17: 0; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 0; 2018-07-27: 0; 2018-07-30: 0; 2018-08-02: 0; 2018-08-03: 0; 2018-08-06: 14.4; 2018-08-09: 28.8; 2018-08-10: 28.8; 2018-08-13: 14.4; 2018-08-14: 0; 2018-08-16: 0; 2018-08-17: 0
Execution - Effort - A TCs in hours | [31 empty] | 2018-07-17: 3.84; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 3.84; 2018-07-27: 0; 2018-07-30: 0; 2018-08-02: 0; 2018-08-03: 3.84; 2018-08-06: 0; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 0; 2018-08-14: 0; 2018-08-16: 0; 2018-08-17: 0
Execution - Effort - P TCs in hours-Auto Hours | [31 empty] | 2018-07-17: 7.68; 2018-07-18: 3.84; 2018-07-19: 3.84; 2018-07-20: 3.84; 2018-07-23: 3.84; 2018-07-24: 3.84; 2018-07-25: 3.84; 2018-07-26: 0; 2018-07-27: 3.84; 2018-07-30: 3.84; 2018-08-02: 3.84; 2018-08-03: 0; 2018-08-06: 11.52; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 11.52; 2018-08-14: 0; 2018-08-16: 3.84; 2018-08-17: 0
FTEs required for test execution and automation verification |  |  |  |  | 6 | 8 | 9 | 13 | 15 | 15 | 16 |  |  |  | 1.7906 | 8.719 | 9.3086 | 9.3086 | 5.821 | 5.821 |  |  |  | 2.327 | 8.7264 | 9.3082 | 9.3082 | 5.8176 | 5.8176 |  |  | 2018-07-17: 2.016; 2018-07-18: 0.72; 2018-07-19: 0.72; 2018-07-20: 0.72; 2018-07-23: 0.72; 2018-07-24: 0.72; 2018-07-25: 0.72; 2018-07-26: 0.288; 2018-07-27: 0.72; 2018-07-30: 0.72; 2018-08-02: 0.72; 2018-08-03: 0.288; 2018-08-06: 2.16; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 2.16; 2018-08-14: 0; 2018-08-16: 0.72; 2018-08-17: 0
Execution - Effort - P TCs in hours-Manual Hours | [31 empty] | 2018-07-17: 28.8; 2018-07-18: 14.4; 2018-07-19: 14.4; 2018-07-20: 14.4; 2018-07-23: 14.4; 2018-07-24: 14.4; 2018-07-25: 14.4; 2018-07-26: 0; 2018-07-27: 14.4; 2018-07-30: 14.4; 2018-08-02: 14.4; 2018-08-03: 0; 2018-08-06: 43.2; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 43.2; 2018-08-14: 0; 2018-08-16: 14.4; 2018-08-17: 0
BA effort Test Data Creation ( Minutes) |  |  | 30 | [9 empty] | 60 | [8 empty] | 60 | [8 empty] | 30
BA efforts in hours |  |  |  | 1.2 | 1.56 | 1.8 | 2.76 | 3 | 3 | 3.24 | 0 |  |  | 0.48 | 1.8 | 1.92 | 1.92 | 1.2 | 1.2 | 0 |  |  | 0.48 | 1.8 | 1.92 | 1.92 | 1.2 | 1.2 | 0 |  |  | 2018-07-17: 10.8; 2018-07-18: 3.6; 2018-07-19: 3.6; 2018-07-20: 3.6; 2018-07-23: 3.6; 2018-07-24: 3.6; 2018-07-25: 3.6; 2018-07-26: 3.6; 2018-07-27: 3.6; 2018-07-30: 3.6; 2018-08-02: 3.6; 2018-08-03: 3.6; 2018-08-06: 14.4; 2018-08-09: 7.2; 2018-08-10: 7.2; 2018-08-13: 14.4; 2018-08-14: 0; 2018-08-16: 3.6; 2018-08-17: 0
Automation execution FTE |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2018-07-17 to 2018-07-20; 2018-07-23
BA FTEs-Total | [31 empty] | 2018-07-17: 1.35; 2018-07-18: 0.45; 2018-07-19: 0.45; 2018-07-20: 0.45; 2018-07-23: 0.45; 2018-07-24: 0.45; 2018-07-25: 0.45; 2018-07-26: 0.45; 2018-07-27: 0.45; 2018-07-30: 0.45; 2018-08-02: 0.45; 2018-08-03: 0.45; 2018-08-06: 1.8; 2018-08-09: 0.9; 2018-08-10: 0.9; 2018-08-13: 1.8; 2018-08-14: 0; 2018-08-16: 0.45; 2018-08-17: 0
Manual FTEs-Total | [31 empty] | 2018-07-17: 3.6; 2018-07-18: 1.8; 2018-07-19: 1.8; 2018-07-20: 1.8; 2018-07-23: 1.8; 2018-07-24: 1.8; 2018-07-25: 1.8; 2018-07-26: 0; 2018-07-27: 1.8; 2018-07-30: 1.8; 2018-08-02: 1.8; 2018-08-03: 0; 2018-08-06: 7.2; 2018-08-09: 3.6; 2018-08-10: 3.6; 2018-08-13: 7.2; 2018-08-14: 0; 2018-08-16: 1.8; 2018-08-17: 0
Automation FTEs-Total | [31 empty] | 2018-07-17: 1.44; 2018-07-18: 0.48; 2018-07-19: 0.48; 2018-07-20: 0.48; 2018-07-23: 0.48; 2018-07-24: 0.48; 2018-07-25: 0.48; 2018-07-26: 0.48; 2018-07-27: 0.48; 2018-07-30: 0.48; 2018-08-02: 0.48; 2018-08-03: 0.48; 2018-08-06: 1.44; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 1.44; 2018-08-14: 0; 2018-08-16: 0.48; 2018-08-17: 0
Partial manual FTEs for auto TCs | [31 empty] | 2018-07-17: 3.6; 2018-07-18: 1.8; 2018-07-19: 1.8; 2018-07-20: 1.8; 2018-07-23: 1.8; 2018-07-24: 1.8; 2018-07-25: 1.8; 2018-07-26: 0; 2018-07-27: 1.8; 2018-07-30: 1.8; 2018-08-02: 1.8; 2018-08-03: 0; 2018-08-06: 5.4; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 5.4; 2018-08-14: 0; 2018-08-16: 1.8; 2018-08-17: 0
Total FTE's |  |  |  | 3.2 | 7.56 | 9.8 | 11.76 | 16 | 18 | 18.24 | 16 |  |  | 0.48 | 3.5906 | 10.639 | 11.2286 | 10.5086 | 7.021 | 5.821 |  |  | 0.48 | 4.127 | 10.6464 | 11.2282 | 10.5082 | 7.0176 | 5.8176 |  |  | 2018-07-17: 6.39; 2018-07-18: 2.73; 2018-07-19: 2.73; 2018-07-20: 2.73; 2018-07-23: 2.73; 2018-07-24: 2.73; 2018-07-25: 2.73; 2018-07-26: 0.93; 2018-07-27: 2.73; 2018-07-30: 2.73; 2018-08-02: 2.73; 2018-08-03: 0.93; 2018-08-06: 10.44; 2018-08-09: 4.5; 2018-08-10: 4.5; 2018-08-13: 10.44; 2018-08-14: 0; 2018-08-16: 2.73; 2018-08-17: 0
Current FTEs(Manual) |  |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  | 2018-07-17: 2; 2018-07-18: 2; 2018-07-19: 2; 2018-07-20: 2; 2018-07-23: 2; 2018-07-24: 2; 2018-07-25: 2; 2018-07-26: 2; 2018-07-27: 2; 2018-07-30: 2; 2018-08-02: 2; 2018-08-03: 2; 2018-08-06: 2; 2018-08-09: 2; 2018-08-10: 2; 2018-08-13: 2; 2018-08-14: 2; 2018-08-16: 2; 2018-08-17: 2
Additional FTEs Required(Manual) |  |  |  | 1.2 | 4.56 | 6.8 | 8.76 | 13 | 12 | 12.24 | 10 |  |  | -1.52 | 0.5906 | 7.639 | 8.2286 | 7.5086 | 1.021 | -0.179 | -6 |  | -1.52 | 1.127 | 7.6464 | 8.2282 | 7.5082 | 1.0176 | -0.1824 | -6 |  | 2018-07-17: 1.6; 2018-07-18: -0.2; 2018-07-19: -0.2; 2018-07-20: -0.2; 2018-07-23: -0.2; 2018-07-24: -0.2; 2018-07-25: -0.2; 2018-07-26: -2; 2018-07-27: -0.2; 2018-07-30: -0.2; 2018-08-02: -0.2; 2018-08-03: -2; 2018-08-06: 5.2; 2018-08-09: 1.6; 2018-08-10: 1.6; 2018-08-13: 5.2; 2018-08-14: -2; 2018-08-16: -0.2; 2018-08-17: -2
Current FTEs(Auto) |  |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  | 2018-07-17: 2; 2018-07-18: 2; 2018-07-19: 2; 2018-07-20: 2; 2018-07-23: 2; 2018-07-24: 2; 2018-07-25: 2; 2018-07-26: 2; 2018-07-27: 2; 2018-07-30: 2; 2018-08-02: 2; 2018-08-03: 2; 2018-08-06: 2; 2018-08-09: 2; 2018-08-10: 2; 2018-08-13: 2; 2018-08-14: 2; 2018-08-16: 2; 2018-08-17: 2
Additional FTEs Required(Auto) |  |  |  | -0.8 | 1.56 | 3.8 | 5.76 | 10 | 6 | 6.24 | 4 |  |  | -3.52 | -2.4094 | 4.639 | 5.2286 | 4.5086 | -4.979 | -6.179 | -12 |  | -3.52 | -1.873 | 4.6464 | 5.2282 | 4.5082 | -4.9824 | -6.1824 | -12 |  | 2018-07-17: -0.56; 2018-07-18: -1.52; 2018-07-19: -1.52; 2018-07-20: -1.52; 2018-07-23: -1.52; 2018-07-24: -1.52; 2018-07-25: -1.52; 2018-07-26: -1.52; 2018-07-27: -1.52; 2018-07-30: -1.52; 2018-08-02: -1.52; 2018-08-03: -1.52; 2018-08-06: -0.56; 2018-08-09: -2; 2018-08-10: -2; 2018-08-13: -0.56; 2018-08-14: -2; 2018-08-16: -1.52; 2018-08-17: -2
Current FTEs(BA Effort) |  |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  | 2018-07-17: 0.5; 2018-07-18: 0.5; 2018-07-19: 0.5; 2018-07-20: 0.5; 2018-07-23: 0.5; 2018-07-24: 0.5; 2018-07-25: 0.5; 2018-07-26: 0.5; 2018-07-27: 0.5; 2018-07-30: 0.5; 2018-08-02: 0.5; 2018-08-03: 0.5; 2018-08-06: 0.5; 2018-08-09: 0.5; 2018-08-10: 0.5; 2018-08-13: 0.5; 2018-08-14: 0.5; 2018-08-16: 0.5; 2018-08-17: 0.5
Additional FTEs Required(BA Effort) |  |  |  | -2.8 | -1.44 | 0.8 | 2.76 | 7 | 0 | 0.24 | -2 |  |  | -5.52 | -5.4094 | 1.639 | 2.2286 | 1.5086 | -10.979 | -12.179 | -18 |  | -5.52 | -4.873 | 1.6464 | 2.2282 | 1.5082 | -10.9824 | -12.1824 | -18 |  | 2018-07-17: -0.85; 2018-07-18: 0.05; 2018-07-19: 0.05; 2018-07-20: 0.05; 2018-07-23: 0.05; 2018-07-24: 0.05; 2018-07-25: 0.05; 2018-07-26: 0.05; 2018-07-27: 0.05; 2018-07-30: 0.05; 2018-08-02: 0.05; 2018-08-03: 0.05; 2018-08-06: -1.3; 2018-08-09: -0.4; 2018-08-10: -0.4; 2018-08-13: -1.3; 2018-08-14: 0.5; 2018-08-16: 0.05; 2018-08-17: 0.5
Note on L19: Stephen Connell (Contractor): Added 1 week due to extension of date for code drop by Development plan submitted 7/12
Note on W19: Stephen Connell (Contractor): Added 1 week due to extension of date for code drop by Development plan submitted 7/12
Note on AH19: Stephen Connell (Contractor): Added 1 week due to extension of date for code drop by Development plan submitted 7/12
Note on A39: Ragavan Sundararajan (Contractor):2 and above WICER looks unrealistic. Need to level set per day
Note on E48: Stephen Connell (Contractor): Hours per test case to provide verification
Note on P48: Stephen Connell (Contractor): Hours per test case to provide verification
Note on AA48: Stephen Connell (Contractor): Hours per test case to provide verification
Note on AK49: Stephen Connell (Contractor): Hours per test case to provide verification
Note on AK50: Ragavan Sundararajan (Contractor): Track lead to validate based on actual trend
Note on D51: Stephen Connell (Contractor): This is the number of Test Cases each tester will be able to complete per day
Note on O51: Stephen Connell (Contractor): This is the number of Test Cases each tester will be able to complete per day
Note on Z51: Stephen Connell (Contractor): This is the number of Test Cases each tester will be able to complete per day
Note on AK51: Stephen Connell (Contractor): This is the number of Test Cases each tester will be able to complete per day
Note on D60: Stephen Connell (Contractor): Number in minutes for a BA on average to complete test data creation for planned test cases submitted for manual or automation
Note on O60: Stephen Connell (Contractor): Number in minutes for a BA on average to complete test data creation for planned test cases submitted for manual or automation
Note on Z60: Stephen Connell (Contractor): Number in minutes for a BA on average to complete test data creation for planned test cases submitted for manual or automation
Note on AK60: Stephen Connell (Contractor): Number in minutes for a BA on average to complete test data creation for planned test cases submitted for manual or automation

## PRJ Plan
PTM per Devesh plan |  |  |  | Summary
|  |  |  | 2018-07-13 | 2018-07-20 | 2018-07-27 | 2018-08-03 | 2018-08-10 | 2018-08-17 | 2018-08-24
Design |  |  |  | 19 | 18 | 12 | 10 | 7 |  |  |  | 66
Test Case Design |  |  |  |  | 104.5 | 99 | 66 | 55 | 38.5 |  |  | 363
Dependency
Execution |  |  |  | WICER | 10 | 13 | 14 | 26 | 28 | 47 |  | 138
|  |  |  | TC | 55 | 71.5 | 77 | 143 | 154 | 258.5 |  | 759
Automation |  |  |  |  | 16.5 | 21.45 | 23.1 | 42.9 | 46.2 | 77.55
Manual Res# |  |  |  | 2 | 38.5 | 50.05 | 53.9 | 100.1 | 107.8 | 180.95
per person per day |  |  |  |  | 3.85 | 5.005 | 5.39 | 10.01 | 10.78 | 18.095
Automation = 30%
Number of TC's per WICER |  |  |  | 5.5
Constrained |  |  |  | 2.5 | 3.08 | 4.004 | 4.312 | 8.008 | 8.624 | 14.476
Input
RTR Track |  |  | PTM Track Plan | [9 empty] | OTC Track Plan | [8 empty] | PRJ Track`
[32 empty] | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 2018-07-21 | 2018-07-22 | 2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-07-26 | 2018-07-27 | 2018-07-28 | 2018-07-29 | 2018-07-30 | 2018-07-31 | 2018-08-01 | 2018-08-02 | 2018-08-03 | 2018-08-04 | 2018-08-05 | 2018-08-06 | 2018-08-07 | 2018-08-08 | 2018-08-09 | 2018-08-10 | 2018-08-11 | 2018-08-12 | 2018-08-13 | 2018-08-14 | 2018-08-15 | 2018-08-16 | 2018-08-17
| Total WICERS | Total executed | Inputs | 2018-07-13 | 2018-07-20 | 2018-07-27 | 2018-08-03 | 2018-08-10 | 2018-08-17 | 2018-08-24 | 2018-08-31 |  | Inputs | 2018-07-13 | 2018-07-20 | 2018-07-27 | 2018-08-03 | 2018-08-10 | 2018-08-17 | 2018-08-24 | 2018-08-31 | Inputs | 2018-07-13 | 2018-07-20 | 2018-07-27 | 2018-08-03 | 2018-08-10 | 2018-08-17 | 2018-08-24 | 2018-08-31 | Inputs | 17-Jul | 18-Jul | 19-Jul | 20-Jul |  |  | 23-Jul | 24-Jul | 25-Jul | 26-Jul | 27-Jul |  |  | 30-Jul | 2018-07-31 | 2018-08-01 | 2-Aug | 3-Aug |  |  | 6-Aug | 2018-08-07 | 2018-08-08 | 9-Aug | 10-Aug |  |  | 13-Aug | 14-Aug | 2018-08-15 | 16-Aug | 17-Aug
CD1.1- WICER Count |  |  |  | 19 | 18 | 12 | 10 | 7 | [23 empty] | 2 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 2 | 2 | 1 | 0 | 2 | 0 | 0 | 1 | 0 | 21
Automation | bar: 2018-07-17; 2018-07-26
Manual | [31 empty] | 2018-08-06: 1; 2018-08-09: 2; 2018-08-10: 2; 2018-08-13: 1
Partial | bar: 2018-07-17 to 2018-07-20; 2018-07-23 to 2018-07-24; 2018-07-30; 2018-08-02; 2018-08-06; 2018-08-08; 2018-08-11; 2018-08-13; 2018-08-16
CD1.2-WICER Count | [31 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2
Automation
Manual
Partial | bar: 2018-07-17; 2018-08-13
CD1.3WICER Count | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8
Automation | bar: 2018-08-03
Manual
Partial | [31 empty] | 2018-07-25: 1; 2018-07-27: 1; 2018-07-31: 1; 2018-08-06: 2; 2018-08-08: 1; 2018-08-13: 1
(blank)
WICERS - Design
Test case design count |  |  |  |  | 104.5 | 99 | 66 | 55 | 38.5
Dependency = Test Data Creation in hrs |  |  |  | 36 | 46.8 | 54 | 82.8 | 90 | 90 | 97.2 | 0 |  |  | 28.8 | 108 | 115.2 | 115.2 | 72 | 72 | 0 | 0 |  | 28.8 | 108 | 115.2 | 115.2 | 72 | 72 | 0 | 0 |  | 2018-07-17: 0; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 0
Execution - WICER# | 155 |  |  |  | 10 | 13 | 15 | 23 | 25 | 25 | 27 |  |  |  | 4 | 15 | 16 | 16 | 10 | 10 |  |  |  | 4 | 15 | 16 | 16 | 10 | 10 |  |  | 3 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 4 | 0 | 2 | 2 | 2 | 1 | 0 | 4 | 0 | 0 | 1 | 0 | 31
Execution - TC # ( Including defect retest of 20%)-M |  |  |  |  | 72 | 93.6 | 108 | 165.6 | 180 | 180 | 194.4 |  |  |  | 28.8 | 108 | 115.2 | 115.2 | 72 | 72 |  |  |  | 28.8 | 108 | 115.2 | 115.2 | 72 | 72 |  |  | 2018-07-17: 0; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 0; 2018-07-27: 0; 2018-07-30: 0; 2018-08-02: 0; 2018-08-03: 0; 2018-08-06: 7.2; 2018-08-09: 14.4; 2018-08-10: 14.4; 2018-08-13: 7.2; 2018-08-14: 0; 2018-08-16: 0; 2018-08-17: 0 | 43.2
Execution - TC # ( Including defect retest of 20%)-A |  |  | 32% |  | 23.04 | 29.952 | 34.56 | 52.992 | 57.6 | 57.6 | 62.208 |  | 63% |  | 18.144 | 34.56 | 36.864 | 36.864 | 23.04 | 23.04 |  | 65% |  | 9.216 | 34.56 | 36.864 | 36.864 | 23.04 | 23.04 |  |  | 2018-07-17: 7.2; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 7.2; 2018-07-27: 0; 2018-07-30: 0; 2018-08-02: 0; 2018-08-03: 7.2; 2018-08-06: 0; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 0; 2018-08-14: 0; 2018-08-16: 0; 2018-08-17: 0 | 21.6
Execution - TC # ( Including defect retest of 20%)-P |  |  | 68% | 2 | 48.96 | 63.648 | 73.44 | 112.608 | 122.4 | 122.4 | 132.192 |  | 37% |  | 10.656 | 73.44 | 78.336 | 78.336 | 48.96 | 48.96 |  | 35% |  | 19.584 | 73.44 | 78.336 | 78.336 | 48.96 | 48.96 |  |  | 2018-07-17: 14.4; 2018-07-18: 7.2; 2018-07-19: 7.2; 2018-07-20: 7.2; 2018-07-23: 7.2; 2018-07-24: 7.2; 2018-07-25: 7.2; 2018-07-26: 0; 2018-07-27: 7.2; 2018-07-30: 7.2; 2018-08-02: 7.2; 2018-08-03: 0; 2018-08-06: 21.6; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 21.6; 2018-08-14: 0; 2018-08-16: 7.2; 2018-08-17: 0 | 129.6
Unconstrained per person per day |  |  |  |  | 4.896 | 6.3648 | 7.344 | 11.2608 | 12.24 | 12.24 | 13.2192 |  |  |  | 1.0656 | 7.344 | 7.8336 | 7.8336 | 4.896 | 4.896 |  |  |  | 1.9584 | 7.344 | 7.8336 | 7.8336 | 4.896 | 4.896 |  |  | 2018-07-18: 0.72; 2018-07-19: 0.72; 2018-07-20: 0.72; 2018-07-23: 0.72; 2018-07-24: 0.72; 2018-07-25: 0.72; 2018-07-26: 0; 2018-07-27: 0.72; 2018-07-30: 0.72; 2018-08-02: 0.72; 2018-08-03: 0; 2018-08-06: 2.16; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 2.16; 2018-08-14: 0; 2018-08-16: 0.72; 2018-08-17: 0
Total TCs | [31 empty] | 21.6 | 7.2 | 7.2 | 7.2 | 0 | 0 | 7.2 | 7.2 | 7.2 | 7.2 | 7.2 | 0 | 0 | 7.2 | 0 | 0 | 7.2 | 7.2 | 0 | 0 | 28.8 | 0 | 0 | 14.4 | 14.4 | 0 | 0 | 28.8 | 0 | 0 | 7.2 | 0 | 194.4
Hours per test case for verification for Partial test cases |  |  | 2 | [9 empty] | 2 | [8 empty] | 2 | [8 empty] | 2
Partial Automation verification hours/week |  |  | 32% | 2 | 37 | 48 | 55 | 85 | 92 | 92 | 100 |  | 63% | 2 | [7 empty] | 65% | 2 | [8 empty] | 2018-07-17: 23.04; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 11.52; 2018-07-27: 0; 2018-07-30: 0; 2018-08-02: 0; 2018-08-03: 11.52; 2018-08-06: 0; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 0; 2018-08-14: 0; 2018-08-16: 0; 2018-08-17: 0
2
Number of TC's per WICER |  |  | 6 | [9 empty] | 6 |  | 29 | 55 | 59 | 59 | 37 | 37 | 0 | 6 |  | 14.7456 | 55.296 | 58.9824 | 58.9824 | 36.864 | 36.864 |  | 6
Productivity test Execution (TC's / Day / person)-M |  |  | 2 | [9 empty] | 2 | [8 empty] | 3 | [8 empty] | 4
Productivity test Execution (TC's / Day / person)-A | [30 empty] | 15
Productivity test Execution (TC's / Day / person)-P | [30 empty] | 4
Execution - Effort - M TCs in hours | [31 empty] | 2018-07-17: 0; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 0; 2018-07-27: 0; 2018-07-30: 0; 2018-08-02: 0; 2018-08-03: 0; 2018-08-06: 14.4; 2018-08-09: 28.8; 2018-08-10: 28.8; 2018-08-13: 14.4; 2018-08-14: 0; 2018-08-16: 0; 2018-08-17: 0
Execution - Effort - A TCs in hours | [31 empty] | 2018-07-17: 3.84; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 3.84; 2018-07-27: 0; 2018-07-30: 0; 2018-08-02: 0; 2018-08-03: 3.84; 2018-08-06: 0; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 0; 2018-08-14: 0; 2018-08-16: 0; 2018-08-17: 0
Execution - Effort - P TCs in hours-Auto Hours | [31 empty] | 2018-07-17: 7.68; 2018-07-18: 3.84; 2018-07-19: 3.84; 2018-07-20: 3.84; 2018-07-23: 3.84; 2018-07-24: 3.84; 2018-07-25: 3.84; 2018-07-26: 0; 2018-07-27: 3.84; 2018-07-30: 3.84; 2018-08-02: 3.84; 2018-08-03: 0; 2018-08-06: 11.52; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 11.52; 2018-08-14: 0; 2018-08-16: 3.84; 2018-08-17: 0
FTEs required for test execution and automation verification |  |  |  |  | 6 | 8 | 9 | 13 | 15 | 15 | 16 |  |  |  | 1.7906 | 8.719 | 9.3086 | 9.3086 | 5.821 | 5.821 |  |  |  | 2.327 | 8.7264 | 9.3082 | 9.3082 | 5.8176 | 5.8176 |  |  | 2018-07-17: 2.016; 2018-07-18: 0.72; 2018-07-19: 0.72; 2018-07-20: 0.72; 2018-07-23: 0.72; 2018-07-24: 0.72; 2018-07-25: 0.72; 2018-07-26: 0.288; 2018-07-27: 0.72; 2018-07-30: 0.72; 2018-08-02: 0.72; 2018-08-03: 0.288; 2018-08-06: 2.16; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 2.16; 2018-08-14: 0; 2018-08-16: 0.72; 2018-08-17: 0
Execution - Effort - P TCs in hours-Manual Hours | [31 empty] | 2018-07-17: 28.8; 2018-07-18: 14.4; 2018-07-19: 14.4; 2018-07-20: 14.4; 2018-07-23: 14.4; 2018-07-24: 14.4; 2018-07-25: 14.4; 2018-07-26: 0; 2018-07-27: 14.4; 2018-07-30: 14.4; 2018-08-02: 14.4; 2018-08-03: 0; 2018-08-06: 43.2; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 43.2; 2018-08-14: 0; 2018-08-16: 14.4; 2018-08-17: 0
BA effort Test Data Creation ( Minutes) |  |  | 30 | [9 empty] | 60 | [8 empty] | 60 | [8 empty] | 30
BA efforts in hours |  |  |  | 1.2 | 1.56 | 1.8 | 2.76 | 3 | 3 | 3.24 | 0 |  |  | 0.48 | 1.8 | 1.92 | 1.92 | 1.2 | 1.2 | 0 |  |  | 0.48 | 1.8 | 1.92 | 1.92 | 1.2 | 1.2 | 0 |  |  | 2018-07-17: 10.8; 2018-07-18: 3.6; 2018-07-19: 3.6; 2018-07-20: 3.6; 2018-07-23: 3.6; 2018-07-24: 3.6; 2018-07-25: 3.6; 2018-07-26: 3.6; 2018-07-27: 3.6; 2018-07-30: 3.6; 2018-08-02: 3.6; 2018-08-03: 3.6; 2018-08-06: 14.4; 2018-08-09: 7.2; 2018-08-10: 7.2; 2018-08-13: 14.4; 2018-08-14: 0; 2018-08-16: 3.6; 2018-08-17: 0
Automation execution FTE |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2018-07-17 to 2018-07-20; 2018-07-23
BA FTEs-Total | [31 empty] | 2018-07-17: 1.35; 2018-07-18: 0.45; 2018-07-19: 0.45; 2018-07-20: 0.45; 2018-07-23: 0.45; 2018-07-24: 0.45; 2018-07-25: 0.45; 2018-07-26: 0.45; 2018-07-27: 0.45; 2018-07-30: 0.45; 2018-08-02: 0.45; 2018-08-03: 0.45; 2018-08-06: 1.8; 2018-08-09: 0.9; 2018-08-10: 0.9; 2018-08-13: 1.8; 2018-08-14: 0; 2018-08-16: 0.45; 2018-08-17: 0
Manual FTEs-Total | [31 empty] | 2018-07-17: 3.6; 2018-07-18: 1.8; 2018-07-19: 1.8; 2018-07-20: 1.8; 2018-07-23: 1.8; 2018-07-24: 1.8; 2018-07-25: 1.8; 2018-07-26: 0; 2018-07-27: 1.8; 2018-07-30: 1.8; 2018-08-02: 1.8; 2018-08-03: 0; 2018-08-06: 7.2; 2018-08-09: 3.6; 2018-08-10: 3.6; 2018-08-13: 7.2; 2018-08-14: 0; 2018-08-16: 1.8; 2018-08-17: 0
Automation FTEs-Total | [31 empty] | 2018-07-17: 1.44; 2018-07-18: 0.48; 2018-07-19: 0.48; 2018-07-20: 0.48; 2018-07-23: 0.48; 2018-07-24: 0.48; 2018-07-25: 0.48; 2018-07-26: 0.48; 2018-07-27: 0.48; 2018-07-30: 0.48; 2018-08-02: 0.48; 2018-08-03: 0.48; 2018-08-06: 1.44; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 1.44; 2018-08-14: 0; 2018-08-16: 0.48; 2018-08-17: 0
Partial manual FTEs for auto TCs | [31 empty] | 2018-07-17: 3.6; 2018-07-18: 1.8; 2018-07-19: 1.8; 2018-07-20: 1.8; 2018-07-23: 1.8; 2018-07-24: 1.8; 2018-07-25: 1.8; 2018-07-26: 0; 2018-07-27: 1.8; 2018-07-30: 1.8; 2018-08-02: 1.8; 2018-08-03: 0; 2018-08-06: 5.4; 2018-08-09: 0; 2018-08-10: 0; 2018-08-13: 5.4; 2018-08-14: 0; 2018-08-16: 1.8; 2018-08-17: 0
Total FTE's |  |  |  | 3.2 | 7.56 | 9.8 | 11.76 | 16 | 18 | 18.24 | 16 |  |  | 0.48 | 3.5906 | 10.639 | 11.2286 | 10.5086 | 7.021 | 5.821 |  |  | 0.48 | 4.127 | 10.6464 | 11.2282 | 10.5082 | 7.0176 | 5.8176 |  |  | 2018-07-17: 6.39; 2018-07-18: 2.73; 2018-07-19: 2.73; 2018-07-20: 2.73; 2018-07-23: 2.73; 2018-07-24: 2.73; 2018-07-25: 2.73; 2018-07-26: 0.93; 2018-07-27: 2.73; 2018-07-30: 2.73; 2018-08-02: 2.73; 2018-08-03: 0.93; 2018-08-06: 10.44; 2018-08-09: 4.5; 2018-08-10: 4.5; 2018-08-13: 10.44; 2018-08-14: 0; 2018-08-16: 2.73; 2018-08-17: 0
Current FTEs(Manual) |  |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  | 2018-07-17: 2; 2018-07-18: 2; 2018-07-19: 2; 2018-07-20: 2; 2018-07-23: 2; 2018-07-24: 2; 2018-07-25: 2; 2018-07-26: 2; 2018-07-27: 2; 2018-07-30: 2; 2018-08-02: 2; 2018-08-03: 2; 2018-08-06: 2; 2018-08-09: 2; 2018-08-10: 2; 2018-08-13: 2; 2018-08-14: 2; 2018-08-16: 2; 2018-08-17: 2
Additional FTEs Required(Manual) |  |  |  | 1.2 | 4.56 | 6.8 | 8.76 | 13 | 12 | 12.24 | 10 |  |  | -1.52 | 0.5906 | 7.639 | 8.2286 | 7.5086 | 1.021 | -0.179 | -6 |  | -1.52 | 1.127 | 7.6464 | 8.2282 | 7.5082 | 1.0176 | -0.1824 | -6 |  | 2018-07-17: 1.6; 2018-07-18: -0.2; 2018-07-19: -0.2; 2018-07-20: -0.2; 2018-07-23: -0.2; 2018-07-24: -0.2; 2018-07-25: -0.2; 2018-07-26: -2; 2018-07-27: -0.2; 2018-07-30: -0.2; 2018-08-02: -0.2; 2018-08-03: -2; 2018-08-06: 5.2; 2018-08-09: 1.6; 2018-08-10: 1.6; 2018-08-13: 5.2; 2018-08-14: -2; 2018-08-16: -0.2; 2018-08-17: -2
Current FTEs(Auto) |  |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  | 2018-07-17: 2; 2018-07-18: 2; 2018-07-19: 2; 2018-07-20: 2; 2018-07-23: 2; 2018-07-24: 2; 2018-07-25: 2; 2018-07-26: 2; 2018-07-27: 2; 2018-07-30: 2; 2018-08-02: 2; 2018-08-03: 2; 2018-08-06: 2; 2018-08-09: 2; 2018-08-10: 2; 2018-08-13: 2; 2018-08-14: 2; 2018-08-16: 2; 2018-08-17: 2
Additional FTEs Required(Auto) |  |  |  | -0.8 | 1.56 | 3.8 | 5.76 | 10 | 6 | 6.24 | 4 |  |  | -3.52 | -2.4094 | 4.639 | 5.2286 | 4.5086 | -4.979 | -6.179 | -12 |  | -3.52 | -1.873 | 4.6464 | 5.2282 | 4.5082 | -4.9824 | -6.1824 | -12 |  | 2018-07-17: -0.56; 2018-07-18: -1.52; 2018-07-19: -1.52; 2018-07-20: -1.52; 2018-07-23: -1.52; 2018-07-24: -1.52; 2018-07-25: -1.52; 2018-07-26: -1.52; 2018-07-27: -1.52; 2018-07-30: -1.52; 2018-08-02: -1.52; 2018-08-03: -1.52; 2018-08-06: -0.56; 2018-08-09: -2; 2018-08-10: -2; 2018-08-13: -0.56; 2018-08-14: -2; 2018-08-16: -1.52; 2018-08-17: -2
Current FTEs(BA Effort) |  |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  | 2018-07-17: 0.5; 2018-07-18: 0.5; 2018-07-19: 0.5; 2018-07-20: 0.5; 2018-07-23: 0.5; 2018-07-24: 0.5; 2018-07-25: 0.5; 2018-07-26: 0.5; 2018-07-27: 0.5; 2018-07-30: 0.5; 2018-08-02: 0.5; 2018-08-03: 0.5; 2018-08-06: 0.5; 2018-08-09: 0.5; 2018-08-10: 0.5; 2018-08-13: 0.5; 2018-08-14: 0.5; 2018-08-16: 0.5; 2018-08-17: 0.5
Additional FTEs Required(BA Effort) |  |  |  | -2.8 | -1.44 | 0.8 | 2.76 | 7 | 0 | 0.24 | -2 |  |  | -5.52 | -5.4094 | 1.639 | 2.2286 | 1.5086 | -10.979 | -12.179 | -18 |  | -5.52 | -4.873 | 1.6464 | 2.2282 | 1.5082 | -10.9824 | -12.1824 | -18 |  | 2018-07-17: -0.85; 2018-07-18: 0.05; 2018-07-19: 0.05; 2018-07-20: 0.05; 2018-07-23: 0.05; 2018-07-24: 0.05; 2018-07-25: 0.05; 2018-07-26: 0.05; 2018-07-27: 0.05; 2018-07-30: 0.05; 2018-08-02: 0.05; 2018-08-03: 0.05; 2018-08-06: -1.3; 2018-08-09: -0.4; 2018-08-10: -0.4; 2018-08-13: -1.3; 2018-08-14: 0.5; 2018-08-16: 0.05; 2018-08-17: 0.5
Note on L19: Stephen Connell (Contractor): Added 1 week due to extension of date for code drop by Development plan submitted 7/12
Note on W19: Stephen Connell (Contractor): Added 1 week due to extension of date for code drop by Development plan submitted 7/12
Note on AH19: Stephen Connell (Contractor): Added 1 week due to extension of date for code drop by Development plan submitted 7/12
Note on A39: Ragavan Sundararajan (Contractor):2 and above WICER looks unrealistic. Need to level set per day
Note on E48: Stephen Connell (Contractor): Hours per test case to provide verification
Note on P48: Stephen Connell (Contractor): Hours per test case to provide verification
Note on AA48: Stephen Connell (Contractor): Hours per test case to provide verification
Note on AK49: Stephen Connell (Contractor): Hours per test case to provide verification
Note on AK50: Ragavan Sundararajan (Contractor): Track lead to validate based on actual trend
Note on D51: Stephen Connell (Contractor): This is the number of Test Cases each tester will be able to complete per day
Note on O51: Stephen Connell (Contractor): This is the number of Test Cases each tester will be able to complete per day
Note on Z51: Stephen Connell (Contractor): This is the number of Test Cases each tester will be able to complete per day
Note on AK51: Stephen Connell (Contractor): This is the number of Test Cases each tester will be able to complete per day
Note on D60: Stephen Connell (Contractor): Number in minutes for a BA on average to complete test data creation for planned test cases submitted for manual or automation
Note on O60: Stephen Connell (Contractor): Number in minutes for a BA on average to complete test data creation for planned test cases submitted for manual or automation
Note on Z60: Stephen Connell (Contractor): Number in minutes for a BA on average to complete test data creation for planned test cases submitted for manual or automation
Note on AK60: Stephen Connell (Contractor): Number in minutes for a BA on average to complete test data creation for planned test cases submitted for manual or automation

## PTP Plan
|  | Priority | (All)
|  | Status | (All)
|  | New/Retrofit/No code change required - Revised | (Multiple Items)
|  | Design / Execution | (Multiple Items) | [30 empty] | PTP | 47
|  | Count of RICEW ID | Column Labels | [30 empty] | PTM | 17
|  | Row Labels | Out of Scope | 2018-07-16 | 2018-07-17 | 2018-07-19 | 2018-07-20 | 2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-07-26 | 2018-07-27 | 2018-07-28 | 2018-07-30 | 2018-07-31 | 2018-08-01 | 2018-08-02 | 2018-08-03 | 2018-08-06 | 2018-08-07 | 2018-08-08 | 2018-08-09 | 2018-08-10 | 2018-08-13 | 2018-08-14 | 2018-08-16 | 2018-08-17 | 2018-08-20 | 2018-08-21 | 2018-08-22 | 2018-08-23 | (blank) | Grand Total
|  | CD1.1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 |  | 1 | 3 | 1 | 1 | 1 | 1 |  | 1 | 3 | 4 | 3 | 4 | 4 | 9 | 4 | 5 | 6 | 4 | 2 |  | 70
|  | Automation | [19 empty] | 1 |  | 1 | 1 | 2 | [6 empty] | 5
|  | Manual | 1 |  | 1 |  | 1 |  |  | 1 |  |  | 1 |  | 1 |  | 1 |  |  | 1 | 1 | 3 |  | 2 | 1 | 4 | 3 | 1 | 1 |  | 2 |  | 26
|  | Partial |  | 1 | 2 | 1 |  | 1 | 3 |  | 1 |  |  | 3 |  | 1 |  | 1 |  |  | 2 |  | 3 | 1 | 2 | 3 | 1 | 4 | 5 | 4 |  |  | 39
|  | CD1.2 |  |  |  | 1 |  |  |  |  | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | 1 | [6 empty] | 1 | 3 | 2 |  |  |  | 14
|  | Manual | [15 empty] | 1 |  | 1 | [8 empty] | 1 |  |  |  | 3
|  | Partial |  |  |  | 1 |  |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  | 1 | [7 empty] | 1 | 3 | 1 |  |  |  | 11
|  | CD1.3 | [9 empty] | 1 |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 1 |  |  | 1 | [8 empty] | 14
|  | Automation | [18 empty] | 1 | [11 empty] | 1
|  | Manual | [13 empty] | 1 | 1 | 1 | 2 | 2 | [12 empty] | 7
|  | Partial | [9 empty] | 1 |  |  | 1 | 1 | 1 | 1 | [5 empty] | 1 | [8 empty] | 6
|  | CD2.1 | [29 empty] | 24 | 24
|  | Automation | [29 empty] | 1 | 1
|  | Manual | [29 empty] | 6 | 6
|  | Partial | [29 empty] | 17 | 17
|  | Grand Total | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 4 | 3 | 3 | 3 | 4 | 3 | 4 | 4 | 4 | 3 | 5 | 4 | 9 | 5 | 8 | 8 | 4 | 2 | 24 | 122
Execution - WICER# | 122 |  | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 4 | 3 | 3 | 3 | 4 | 3 | 4 | 4 | 4 | 3 | 5 | 4 | 9 | 5 | 8 | 8 | 4 | 2 | 24 | 122
Execution - TC # ( Including defect retest of 20%)-M |  | 0 | 7.2 | 0 | 7.2 | 0 | 7.2 | 0 | 0 | 7.2 | 0 | 0 | 7.2 | 0 | 7.2 | 7.2 | 14.4 | 14.4 | 14.4 | 28.8 | 7.2 | 21.6 | 0 | 14.4 | 7.2 | 28.8 | 21.6 | 7.2 | 14.4 | 0 | 14.4 | 0 | 259.2
Execution - TC # ( Including defect retest of 20%)-A | 32% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2 | 7.2 | 0 | 7.2 | 7.2 | 14.4 | 0 | 0 | 0 | 0 | 0 | 0 | 43.2
Execution - TC # ( Including defect retest of 20%)-P | 68% |  | 0 | 7.2 | 14.4 | 14.4 | 0 | 7.2 | 21.6 | 0 | 14.4 | 14.4 | 0 | 28.8 | 14.4 | 14.4 | 7.2 | 14.4 | 7.2 | 0 | 14.4 | 0 | 21.6 | 14.4 | 14.4 | 21.6 | 14.4 | 50.4 | 43.2 | 28.8 | 0 | 0 | 403.2
Update Row 27,28,29 with actual test case count
Hours per test case for verification for Partial test cases | 2
Number of TC's per WICER | 6
Productivity test Execution (TC's / Day / person)-M | 4
Productivity test Execution (TC's / Day / person)-A | 15
Productivity test Execution (TC's / Day / person)-P | 4
Execution - Effort - M TCs in hours |  |  | 14.4 | 0 | 14.4 | 0 | 14.4 | 0 | 0 | 14.4 | 0 | 0 | 14.4 | 0 | 14.4 | 14.4 | 28.8 | 28.8 | 28.8 | 57.6 | 14.4 | 43.2 | 0 | 28.8 | 14.4 | 57.6 | 43.2 | 14.4 | 28.8 | 0 | 28.8 | 0 | 518.4
Execution - Effort - A TCs in hours |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.84 | 3.84 | 0 | 3.84 | 3.84 | 7.68 | 0 | 0 | 0 | 0 | 0 | 0 | 23.04
Execution - Effort - P TCs in hours-Auto Hours |  |  | 0 | 3.84 | 7.68 | 7.68 | 0 | 3.84 | 11.52 | 0 | 7.68 | 7.68 | 0 | 15.36 | 7.68 | 7.68 | 3.84 | 7.68 | 3.84 | 0 | 7.68 | 0 | 11.52 | 7.68 | 7.68 | 11.52 | 7.68 | 26.88 | 23.04 | 15.36 | 0 | 0 | 215.04
Execution - Effort - P TCs in hours-Manual Hours |  |  | 0 | 7.68 | 15.36 | 15.36 | 0 | 7.68 | 23.04 | 0 | 15.36 | 15.36 | 0 | 30.72 | 15.36 | 15.36 | 7.68 | 15.36 | 7.68 | 0 | 15.36 | 0 | 23.04 | 15.36 | 15.36 | 23.04 | 15.36 | 53.76 | 46.08 | 30.72 | 0 | 0 | 430.08
BA effort Test Data Creation ( Minutes) | 30
BA efforts in hours |  |  | 3.6 | 3.6 | 10.8 | 7.2 | 3.6 | 3.6 | 10.8 | 3.6 | 7.2 | 7.2 | 3.6 | 14.4 | 10.8 | 10.8 | 10.8 | 14.4 | 10.8 | 14.4 | 14.4 | 14.4 | 10.8 | 18 | 14.4 | 32.4 | 18 | 28.8 | 28.8 | 14.4 | 7.2 | 0 | 352.8
BA FTEs |  |  | 0.45 | 0.45 | 1.35 | 0.9 | 0.45 | 0.45 | 1.35 | 0.45 | 0.9 | 0.9 | 0.45 | 1.8 | 1.35 | 1.35 | 1.35 | 1.8 | 1.35 | 1.8 | 1.8 | 1.8 | 1.35 | 2.25 | 1.8 | 4.05 | 2.25 | 3.6 | 3.6 | 1.8 | 0.9 | 0 | 44.1
Manual FTEs |  |  | 1.8 | 0.96 | 3.72 | 1.92 | 1.8 | 0.96 | 2.88 | 1.8 | 1.92 | 1.92 | 1.8 | 3.84 | 3.72 | 3.72 | 4.56 | 5.52 | 4.56 | 7.2 | 3.72 | 5.4 | 2.88 | 5.52 | 3.72 | 10.08 | 7.32 | 8.52 | 9.36 | 3.84 | 3.6 | 0 | 118.56
Automation FTEs |  |  | 0 | 0.48 | 0.96 | 0.96 | 0 | 0.48 | 1.44 | 0 | 0.96 | 0.96 | 0 | 1.92 | 0.96 | 0.96 | 0.48 | 0.96 | 0.48 | 0 | 1.44 | 0.48 | 1.44 | 1.44 | 1.44 | 2.4 | 0.96 | 3.36 | 2.88 | 1.92 | 0 | 0 | 29.76
Total FTE's |  |  | 2.25 | 1.89 | 6.03 | 3.78 | 2.25 | 1.89 | 5.67 | 2.25 | 3.78 | 3.78 | 2.25 | 7.56 | 6.03 | 6.03 | 6.39 | 8.28 | 6.39 | 9 | 6.96 | 7.68 | 5.67 | 9.21 | 6.96 | 16.53 | 10.53 | 15.48 | 15.84 | 7.56 | 4.5 | 0 | 192.42
Current FTEs(Manual) |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6
Addition FTEs Required(Manual) |  |  | 0.25 | -0.11 | 4.03 | 1.78 | 0.25 | -0.11 | 0.67 | -2.75 | -1.22 | -1.22 | -2.75 | 2.56 | 1.03 | 1.03 | 1.39 | 3.28 | 1.39 | 4 | 1.96 | 2.68 | 0.67 | 1.21 | -1.04 | 8.53 | 2.53 | 7.48 | 7.84 | -0.44 | -3.5 | -6 | 186.42
Current FTEs(Auto) |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6
Addition FTEs Required(Auto) |  |  | -1 | -0.52 | -0.04 | -0.04 | -1 | -0.52 | 0.44 | -1 | -0.04 | -0.04 | -1 | 0.92 | -0.04 | -0.04 | -0.52 | -0.04 | -0.52 | -1 | 0.44 | -0.52 | 0.44 | 0.44 | 0.44 | 1.4 | -0.04 | 2.36 | 1.88 | 0.92 | -1 | -6 | 180.42
Current FTEs(BA Effort) |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6
Addition FTEs Required(BA Effort) |  |  | -0.55 | -0.55 | 0.35 | -0.1 | -0.55 | -0.55 | 0.35 | -0.55 | -0.1 | -0.1 | -0.55 | 0.8 | 0.35 | 0.35 | 0.35 | 0.8 | 0.35 | 0.8 | 0.8 | 0.8 | 0.35 | 1.25 | 0.8 | 3.05 | 1.25 | 2.6 | 2.6 | 0.8 | -0.1 | -1 | 174.42
Note on A26: Ragavan Sundararajan (Contractor):2 and above WICER looks unrealistic. Need to level set per day
Note on B33: Stephen Connell (Contractor): This is the number of Test Cases each tester will be able to complete per day
Note on O33: Stephen Connell (Contractor): This is the number of Test Cases each tester will be able to complete per day
Note on Z33: Stephen Connell (Contractor): This is the number of Test Cases each tester will be able to complete per day
Note on O41: Stephen Connell (Contractor): Number in minutes for a BA on average to complete test data creation for planned test cases submitted for manual or automation
Note on Z41: Stephen Connell (Contractor): Number in minutes for a BA on average to complete test data creation for planned test cases submitted for manual or automation

## PTM Plan
PTM per Devesh plan |  |  |  | Summary
|  |  |  | 2018-07-13 | 2018-07-20 | 2018-07-27 | 2018-08-03 | 2018-08-10 | 2018-08-17 | 2018-08-24
Design |  |  |  | 19 | 18 | 12 | 10 | 7 |  |  |  | 66
Test Case Design |  |  |  |  | 104.5 | 99 | 66 | 55 | 38.5 |  |  | 363
Dependency
Execution |  |  |  | WICER | 10 | 13 | 14 | 26 | 28 | 47 |  | 138
|  |  |  | TC | 55 | 71.5 | 77 | 143 | 154 | 258.5 |  | 759
Automation |  |  |  |  | 16.5 | 21.45 | 23.1 | 42.9 | 46.2 | 77.55
Manual Res# |  |  |  | 2 | 38.5 | 50.05 | 53.9 | 100.1 | 107.8 | 180.95
per person per day |  |  |  |  | 3.85 | 5.005 | 5.39 | 10.01 | 10.78 | 18.095
Automation = 30%
Number of TC's per WICER |  |  |  | 5.5
Constrained |  |  |  | 2.5 | 3.08 | 4.004 | 4.312 | 8.008 | 8.624 | 14.476
Input
PTM Track |  |  | PTM Track Plan | [9 empty] | OTC Track Plan | [8 empty] | PRJ Track`
 | time axis 2018-07-16 to 2018-08-31
| Total WICERS | Total executed | Inputs | 2018-07-13 | 2018-07-20 | 2018-07-27 | 2018-08-03 | 2018-08-10 | 2018-08-17 | 2018-08-24 | 2018-08-31 |  | Inputs | 2018-07-13 | 2018-07-20 | 2018-07-27 | 2018-08-03 | 2018-08-10 | 2018-08-17 | 2018-08-24 | 2018-08-31 | Inputs | 2018-07-13 | 2018-07-20 | 2018-07-27 | 2018-08-03 | 2018-08-10 | 2018-08-17 | 2018-08-24 | 2018-08-31 | Inputs | 2018-07-16: 17-Jul; 2018-07-18: 18-Jul; 2018-07-19: 19-Jul; 2018-07-20: 20-Jul; 2018-07-23: 23-Jul; 2018-07-24: 24-Jul; 2018-07-25: 25-Jul; 2018-07-26: 26-Jul; 2018-07-27: 27-Jul; 2018-07-30: 30-Jul; 2018-07-31: 2018-07-31; 2018-08-01: 2018-08-01; 2018-08-02: 2-Aug; 2018-08-03: 3-Aug; 2018-08-06: 6-Aug; 2018-08-07: 2018-08-07; 2018-08-08: 2018-08-08; 2018-08-09: 9-Aug; 2018-08-10: 10-Aug; 2018-08-13: 13-Aug; 2018-08-14: 14-Aug; 2018-08-15: 2018-08-15; 2018-08-16: 16-Aug; 2018-08-17: 17-Aug
CD1.1 |  |  |  | 19 | 18 | 12 | 10 | 7 | [23 empty] | 1 | 3 | 1 | 2 | 1 | 0 | 0 | 2 | 2 | 2 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 1 | 4 | 0 | 0 | 2 | 2 | 3 | 0 | 3 | 0 | 0 | 4 | 6 | 0 | 6 | 7 | 0 | 0 | 5 | 7 | 5 | 5 | 6 | 0 | 0 | 5 | 6 | 5 | 0 | 0
Automation
Manual | [31 empty] | 2018-07-16: 1; 2018-07-17: 3; 2018-07-24: 1; 2018-07-26: 1; 2018-07-30: 2; 2018-07-31: 2; 2018-08-02: 1; 2018-08-03: 4; 2018-08-06: 2; 2018-08-07: 2; 2018-08-08: 3; 2018-08-10: 2; 2018-08-13: 1; 2018-08-14: 6; 2018-08-16: 5; 2018-08-21: 1; 2018-08-22: 1; 2018-08-23: 2; 2018-08-24: 3; 2018-08-28: 2; 2018-08-29: 2
Partial | [31 empty] | 2018-07-18: 1; 2018-07-19: 2; 2018-07-20: 1; 2018-07-23: 2; 2018-07-24: 1; 2018-07-25: 2; 2018-07-26: 2; 2018-08-01: 2; 2018-08-10: 1; 2018-08-13: 3; 2018-08-16: 1; 2018-08-17: 7; 2018-08-20: 5; 2018-08-21: 6; 2018-08-22: 4; 2018-08-23: 3; 2018-08-24: 3; 2018-08-27: 5; 2018-08-28: 4; 2018-08-29: 3
CD1.2 | [31 empty] | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 3 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Automation
Manual | [31 empty] | 2018-07-16: 2
Partial | [31 empty] | 2018-07-18: 1; 2018-07-20: 1; 2018-07-23: 3; 2018-07-24: 2; 2018-07-27: 1; 2018-07-30: 1; 2018-08-10: 1; 2018-08-20: 1; 2018-08-23: 1
CD1.3 | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 2 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Automation
Manual | bar: 2018-08-23
Partial | [31 empty] | 2018-07-27: 1; 2018-07-30: 1; 2018-08-01: 2; 2018-08-02: 3; 2018-08-06: 2; 2018-08-07: 2; 2018-08-13: 2; 2018-08-16: 1
(blank)
WICERS - Design
Test case design count |  |  |  |  | 104.5 | 99 | 66 | 55 | 38.5
Dependency = Test Data Creation in hrs |  |  |  | 36 | 46.8 | 54 | 82.8 | 90 | 90 | 97.2 | 0 |  |  | 28.8 | 108 | 115.2 | 115.2 | 72 | 72 | 0 | 0 |  | 28.8 | 108 | 115.2 | 115.2 | 72 | 72 | 0 | 0 |  | 2018-07-16: 1; 2018-07-18: 1; 2018-07-19: 1; 2018-07-20: 2; 2018-07-23: 5; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 1
Execution - WICER# | 155 |  |  |  | 10 | 13 | 15 | 23 | 25 | 25 | 27 |  |  |  | 4 | 15 | 16 | 16 | 10 | 10 |  |  |  | 4 | 15 | 16 | 16 | 10 | 10 |  |  | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 5 | 4 | 2 | 3 | 2 | 0 | 0 | 4 | 2 | 4 | 4 | 4 | 0 | 0 | 4 | 4 | 3 | 0 | 4 | 0 | 0 | 6 | 6 | 0 | 7 | 7 | 0 | 0 | 6 | 7 | 5 | 7 | 6 | 0 | 0 | 5 | 6 | 5 | 0 | 0
Execution - TC # -M |  |  |  |  | 72 | 93.6 | 108 | 165.6 | 180 | 180 | 194.4 |  |  |  | 28.8 | 108 | 115.2 | 115.2 | 72 | 72 |  |  |  | 28.8 | 108 | 115.2 | 115.2 | 72 | 72 |  |  | 19 | 11 | 1 | 1 | 1 | 0 | 0 | 2 | 5 | 0 | 0 | 1 | 0 | 0 | 8 | -1 | 0 | 10 | 28 | 0 | 0 | 14 | 16 | 21 | 0 | 9 | 0 | 0 | 8 | 37 | 0 | 45 | 1 | 0 | 0 | 0 | 9 | 28 | 16 | 24 | 0 | 0 | 0 | 22 | 14 | 0 | 0
Execution - TC # - A |  |  | 32% |  | 23.04 | 29.952 | 34.56 | 52.992 | 57.6 | 57.6 | 62.208 |  | 63% |  | 18.144 | 34.56 | 36.864 | 36.864 | 23.04 | 23.04 |  | 65% |  | 9.216 | 34.56 | 36.864 | 36.864 | 23.04 | 23.04 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 0 | 8 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0
Execution - TC # - P |  |  | 68% | 2 | 48.96 | 63.648 | 73.44 | 112.608 | 122.4 | 122.4 | 132.192 |  | 37% |  | 10.656 | 73.44 | 78.336 | 78.336 | 48.96 | 48.96 |  | 35% |  | 19.584 | 73.44 | 78.336 | 78.336 | 48.96 | 48.96 |  |  | 0 | 0 | 8 | 15 | 12 | 0 | 0 | 21 | 4 | 0 | 7 | 6 | 0 | 0 | 7 | -6 | 10 | 15 | 0 | 0 | 0 | 10 | 12 | 0 | 0 | 11 | 0 | 0 | 26 | 0 | 0 | 10 | 32 | 0 | 0 | 30 | 35 | 26 | 25 | 14 | 0 | 0 | 34 | 12 | 10 | 0 | 0
Unconstrained per person per day |  |  |  |  | 4.896 | 6.3648 | 7.344 | 11.2608 | 12.24 | 12.24 | 13.2192 |  |  |  | 1.0656 | 7.344 | 7.8336 | 7.8336 | 4.896 | 4.896 |  |  |  | 1.9584 | 7.344 | 7.8336 | 7.8336 | 4.896 | 4.896
Total TCs | [31 empty] | 19 | 11 | 9 | 16 | 13 | 0 | 0 | 23 | 9 | 0 | 7 | 7 | 0 | 0 | 15 | -7 | 14 | 31 | 28 | 0 | 0 | 28 | 28 | 21 | 0 | 22 | 0 | 0 | 42 | 37 | 0 | 59 | 33 | 0 | 0 | 30 | 44 | 54 | 45 | 40 | 0 | 0 | 34 | 34 | 26 | 0 | 0
[53 empty] | update actual TCs(row 40,41,42) from tracker if Or level set the TCs for the day. This is crowded. | [6 empty] | update actual TCs(row 40,41,42) from tracker if Or level set the TCs for the day. This is crowded.
Hours per test case for verification for Partial test cases |  |  | 2 | [9 empty] | 2 | [8 empty] | 2 | [8 empty] | 2
Partial Automation verification hours/week |  |  | 32% | 2 | 37 | 48 | 55 | 85 | 92 | 92 | 100 |  | 63% | 2 | [7 empty] | 65% | 2 | [8 empty] | 2018-07-16: 0; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 0; 2018-07-27: 0; 2018-07-30: 0; 2018-08-02: 9.6; 2018-08-03: 0; 2018-08-06: 6.4; 2018-08-09: 0; 2018-08-10: 3.2; 2018-08-13: 12.8; 2018-08-14: 0; 2018-08-31: 0
2
Number of TC's per WICER |  |  | 6 | [9 empty] | 6 |  | 29 | 55 | 59 | 59 | 37 | 37 | 0 | 6 |  | 14.7456 | 55.296 | 58.9824 | 58.9824 | 36.864 | 36.864 |  | 6
Productivity test Execution (TC's / Day / person)-M |  |  | 2 | [9 empty] | 2 | [8 empty] | 3 | [8 empty] | 4
Productivity test Execution (TC's / Day / person)-A | [30 empty] | 15
Productivity test Execution (TC's / Day / person)-P | [30 empty] | 4
Execution - Effort - M TCs in hours | [31 empty] | 38 | 22 | 2 | 2 | 2 | 0 | 0 | 4 | 10 | 0 | 0 | 2 | 0 | 0 | 16 | -2 | 0 | 20 | 56 | 0 | 0 | 28 | 32 | 42 | 0 | 18 | 0 | 0 | 16 | 74 | 0 | 90 | 2 | 0 | 0 | 0 | 18 | 56 | 32 | 48 | 0 | 0 | 0 | 44 | 28 | 0 | 0
Execution - Effort - A TCs in hours | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1333 | 3.2 | 0 | 0 | 0 | 2.1333 | 0 | 0 | 0 | 1.0667 | 0 | 0 | 4.2667 | 0 | 0 | 2.1333 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1333 | 1.0667 | 0 | 0 | 0 | 0 | 1.0667 | 0 | 0
Execution - Effort - P TCs in hours-Auto Hours | [31 empty] | 0 | 0 | 4.2667 | 8 | 6.4 | 0 | 0 | 11.2 | 2.1333 | 0 | 3.7333 | 3.2 | 0 | 0 | 3.7333 | -3.2 | 5.3333 | 8 | 0 | 0 | 0 | 5.3333 | 6.4 | 0 | 0 | 5.8667 | 0 | 0 | 13.8667 | 0 | 0 | 5.3333 | 17.0667 | 0 | 0 | 16 | 18.6667 | 13.8667 | 13.3333 | 7.4667 | 0 | 0 | 18.1333 | 6.4 | 5.3333 | 0 | 0
FTEs required for test execution and automation verification |  |  |  |  | 6 | 8 | 9 | 13 | 15 | 15 | 16 |  |  |  | 1.7906 | 8.719 | 9.3086 | 9.3086 | 5.821 | 5.821 |  |  |  | 2.327 | 8.7264 | 9.3082 | 9.3082 | 5.8176 | 5.8176 |  |  | 0 | 0 | 0.8 | 1.5 | 1.2 | 0 | 0 | 2.1 | 0.4 | 0 | 0.7 | 0.6 | 0 | 0 | 0.7 | -0.6 | 1 | 1.74 | 0 | 0 | 0 | 1.16 | 1.2 | 0 | 0 | 1.18 | 0 | 0 | 2.92 | 0 | 0 | 1 | 3.2 | 0 | 0 | 3 | 3.5 | 2.6 | 2.5 | 1.4 | 0 | 0 | 3.4 | 1.2 | 1 | 0 | 0
Execution - Effort - P TCs in hours-Manual Hours | [31 empty] | 0 | 0 | 16 | 30 | 24 | 0 | 0 | 42 | 8 | 0 | 14 | 12 | 0 | 0 | 14 | -12 | 20 | 30 | 0 | 0 | 0 | 20 | 24 | 0 | 0 | 22 | 0 | 0 | 52 | 0 | 0 | 20 | 64 | 0 | 0 | 60 | 70 | 52 | 50 | 28 | 0 | 0 | 68 | 24 | 20 | 0 | 0
Defect Retest Effort - Manual | [31 empty] | 4.8 | 8 | 8 | 8 | 8 | 0 | 0 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 0 | 0 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 0 | 0 | 9.6 | 9.6 | 9.6 | 9.6 | 9.6 | 0 | 0 | 14.4 | 14.4 | 11.2 | 14.4 | 14.4 | 0 | 0 | 14.4 | 14.4 | 14.4 | 14.4 | 14.4 | 0 | 0 | 14.4 | 14.4 | 14.4 | 14.4 | 14.4
Defect Retest Effort - Auto | [31 empty] | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 0 | 0 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 0 | 0 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 0 | 0 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 0 | 0 | 3.2 | 3.2 | 0 | 3.2 | 3.2 | 0 | 0 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 0 | 0 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2
BA effort Test Data Creation ( Minutes) |  |  | 30 | [9 empty] | 60 | [8 empty] | 60 | [8 empty] | 30
BA efforts in hours |  |  |  | 1.2 | 1.56 | 1.8 | 2.76 | 3 | 3 | 3.24 | 0 |  |  | 0.48 | 1.8 | 1.92 | 1.92 | 1.2 | 1.2 | 0 |  |  | 0.48 | 1.8 | 1.92 | 1.92 | 1.2 | 1.2 | 0 |  |  | 9.5 | 5.5 | 4.5 | 8 | 6.5 | 0 | 0 | 11.5 | 4.5 | 0 | 3.5 | 3.5 | 0 | 0 | 7.5 | -3.5 | 7 | 15.5 | 14 | 0 | 0 | 14 | 14 | 10.5 | 0 | 11 | 0 | 0 | 21 | 18.5 | 0 | 29.5 | 16.5 |  |  | 15 | 22 | 27 | 22.5 | 20 |  |  | 17 | 17 | 13 | 0 | 0 | 386
Automation execution FTE |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2018-07-16; 2018-07-18 to 2018-07-20; 2018-07-23
BA FTEs-Total | [31 empty] | 1.1875 | 0.6875 | 0.5625 | 1 | 0.8125 |  |  | 1.4375 | 0.5625 | 0 | 0.4375 | 0.4375 |  |  | 0.9375 | -0.4375 | 0.875 | 1.9375 | 1.75 |  |  | 1.75 | 1.75 | 1.3125 | 0 | 1.375 |  |  | 2.625 | 2.3125 |  | 3.6875 | 2.0625 |  |  | 1.875 | 2.75 | 3.375 | 2.8125 | 2.5 |  |  | 2.125 | 2.125 | 1.625 | 0 | 0 | 48.25
Manual FTEs-Total | [31 empty] | 5.35 | 3.75 | 3.25 | 5 | 4.25 | 0 | 0 | 6.95 | 3.45 | 1.2 | 2.95 | 2.95 | 0 | 0 | 4.95 | -0.55 | 3.7 | 7.45 | 8.2 | 0 | 0 | 7.2 | 8.2 | 6.45 | 1.2 | 6.2 | 0 | 0 | 10.3 | 11.05 | 1.4 | 15.55 | 10.05 |  |  | 9.3 | 12.8 | 15.3 | 12.05 | 11.3 |  |  | 10.3 | 10.3 | 7.8 | 1.8 | 1.8 | 233.2
Automation FTEs-Total | [31 empty] | 0.4 | 0.4 | 0.93333 | 1.4 | 1.2 | 0 | 0 | 1.8 | 0.66667 | 0.4 | 0.86667 | 0.8 | 0 | 0 | 0.86667 | 0 | 1.3333 | 1.8 | 0.4 | 0 | 0 | 1.3333 | 1.2 | 0.4 | 0.4 | 1.2667 | 0 | 0 | 2.6667 | 0.4 | 0 | 1.3333 | 2.5333 |  |  | 2.4 | 2.7333 | 2.1333 | 2.3333 | 1.4667 |  |  | 2.6667 | 1.2 | 1.2 | 0.4 | 0.4 | 41.7333
Partial manual FTEs for auto TCs | [31 empty] | 0 | 0 | 2 | 3.75 | 3 |  |  | 5.25 | 1 | 0 | 1.75 | 1.5 |  |  | 1.75 | -1.5 | 2.5 | 3.75 | 0 |  |  | 2.5 | 3 | 0 | 0 | 2.75 |  |  | 6.5 | 0 |  | 2.5 | 8 |  |  | 7.5 | 8.75 | 6.5 | 6.25 | 3.5 |  |  | 8.5 | 3 | 2.5 | 0 | 0
Total FTE's |  |  |  | 3.2 | 7.56 | 9.8 | 11.76 | 16 | 18 | 18.24 | 16 |  |  | 0.48 | 3.5906 | 10.639 | 11.2286 | 10.5086 | 7.021 | 5.821 |  |  | 0.48 | 4.127 | 10.6464 | 11.2282 | 10.5082 | 7.0176 | 5.8176 |  |  | 6.9375 | 4.8375 | 4.7458 | 7.4 | 6.2625 |  |  | 10.1875 | 4.6792 | 1.6 | 4.2542 | 4.1875 |  |  | 6.7542 | -0.9875 | 5.9083 | 11.1875 | 10.35 |  |  | 10.2833 | 11.15 | 8.1625 | 1.6 | 8.8417 |  |  | 15.5917 | 13.7625 |  | 20.5708 | 14.6458 |  |  | 13.575 | 18.2833 | 20.8083 | 17.1958 | 15.2667 |  |  | 15.0917 | 13.625 | 10.625 | 2.2 | 2.2 | 321.7833
Current FTEs(Manual) |  |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  | 3 | 3 | 3 | 3 | 3 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 7 | 7 | 7 | 7 | 7 |  |  | 7 | 7 | 7 | 7 | 7 |  |  | 7 | 7 | 7 | 7 | 7 | 180
Additional FTEs Required(Manual) |  |  |  | 1.2 | 4.56 | 6.8 | 8.76 | 13 | 12 | 12.24 | 10 |  |  | -1.52 | 0.5906 | 7.639 | 8.2286 | 7.5086 | 1.021 | -0.179 | -6 |  | -1.52 | 1.127 | 7.6464 | 8.2282 | 7.5082 | 1.0176 | -0.1824 | -6 |  | 2.35 | 0.75 | 0.25 | 2 | 1.25 |  |  | 2.95 | -0.55 | -2.8 | -1.05 | -1.05 |  |  | 0.95 | -4.55 | -0.3 | 3.45 | 4.2 |  |  | 3.2 | 4.2 | 2.45 | -2.8 | 2.2 |  |  | 3.3 | 4.05 |  | 8.55 | 3.05 |  |  | 2.3 | 5.8 | 8.3 | 5.05 | 4.3 |  |  | 3.3 | 3.3 | 0.8 | -5.2 | -5.2 | 58.8
Current FTEs(Auto) |  |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 68
Additional FTEs Required(Auto) |  |  |  | -0.8 | 1.56 | 3.8 | 5.76 | 10 | 6 | 6.24 | 4 |  |  | -3.52 | -2.4094 | 4.639 | 5.2286 | 4.5086 | -4.979 | -6.179 | -12 |  | -3.52 | -1.873 | 4.6464 | 5.2282 | 4.5082 | -4.9824 | -6.1824 | -12 |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | -1.1333 | -1.2 |  |  | -1.1333 | -2 | -0.66667 | -0.2 | -1.6 |  |  | -0.66667 | -0.8 | -1.6 | -1.6 | -0.73333 |  |  | 0.66667 | -1.6 |  | -0.66667 | 0.53333 |  |  | 0.4 | 0.73333 | 0.13333 | 0.33333 | -0.53333 |  |  | 0.66667 | -0.8 | -0.8 | -1.6 | -1.6 | -9.4667
Current FTEs(BA Effort) |  |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 |  | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 | [48 empty] | 34 | bar: 2018-07-16 to 2018-07-20; 2018-07-23 to 2018-07-27; 2018-07-30 to 2018-08-03; 2018-08-06 to 2018-08-10; 2018-08-13 to 2018-08-14; 2018-08-16 to 2018-08-17; 2018-08-20 to 2018-08-24; 2018-08-27 to 2018-08-31
Additional FTEs Required(BA Effort) |  |  |  | -2.8 | -1.44 | 0.8 | 2.76 | 7 | 0 | 0.24 | -2 |  |  | -5.52 | -5.4094 | 1.639 | 2.2286 | 1.5086 | -10.979 | -12.179 | -18 |  | -5.52 | -4.873 | 1.6464 | 2.2282 | 1.5082 | -10.9824 | -12.1824 | -18 |  | 0.1875 | -0.3125 | -0.4375 | 0 | -0.1875 |  |  | 0.4375 | -0.4375 | -1 | -0.5625 | -0.5625 |  |  | -0.0625 | -1.4375 | -0.125 | 0.9375 | 0.75 |  |  | 0.75 | 0.75 | 0.3125 | -1 | 0.375 |  |  | 1.625 | 1.3125 |  | 2.6875 | 1.0625 |  |  | 0.875 | 1.75 | 2.375 | 1.8125 | 1.5 |  |  | 1.125 | 1.125 | 0.625 | -1 | -1 | 14.25
Current FTE | [31 empty] | 6 | 6 | 6 | 6 | 6 |  |  | 7 | 7 | 7 | 7 | 7 |  |  | 7 | 7 | 7 | 7 | 7 |  |  | 7 | 7 | 7 | 7 | 7 |  |  | 10 | 10 |  | 10 | 10 |  |  | 10 | 10 | 10 | 10 | 10 |  |  | 10 | 10 | 10 | 10 | 10 | 275
Additional FTE needed (Overall) | [31 empty] | 0.9375 | -1.1625 | -1.2542 | 1.4 | 0.2625 |  |  | 3.1875 | -2.3208 | -5.4 | -2.7458 | -2.8125 |  |  | -0.24583 | -7.9875 | -1.0917 | 4.1875 | 3.35 |  |  | 3.2833 | 4.15 | 1.1625 | -5.4 | 1.8417 |  |  | 5.5917 | 3.7625 |  | 10.5708 | 4.6458 |  |  | 3.575 | 8.2833 | 10.8083 | 7.1958 | 5.2667 |  |  | 5.0917 | 3.625 | 0.625 | -7.8 | -7.8 | 46.7833
[36 empty] | 0.18333 | [6 empty] | -10.0917 | [6 empty] | -1.7875 | [6 empty] | 5.0375 | [13 empty] | 35.1292 | [6 empty] | -6.2583
Note on L19: Stephen Connell (Contractor): Added 1 week due to extension of date for code drop by Development plan submitted 7/12
Note on W19: Stephen Connell (Contractor): Added 1 week due to extension of date for code drop by Development plan submitted 7/12
Note on AH19: Stephen Connell (Contractor): Added 1 week due to extension of date for code drop by Development plan submitted 7/12
Note on A39: Ragavan Sundararajan (Contractor):2 and above WICER looks unrealistic. Need to level set per day
Note on E48: Stephen Connell (Contractor): Hours per test case to provide verification
Note on P48: Stephen Connell (Contractor): Hours per test case to provide verification
Note on AA48: Stephen Connell (Contractor): Hours per test case to provide verification
Note on AK49: Stephen Connell (Contractor): Hours per test case to provide verification
Note on AK50: Ragavan Sundararajan (Contractor): Track lead to validate based on actual trend
Note on D51: Stephen Connell (Contractor): This is the number of Test Cases each tester will be able to complete per day
Note on O51: Stephen Connell (Contractor): This is the number of Test Cases each tester will be able to complete per day
Note on Z51: Stephen Connell (Contractor): This is the number of Test Cases each tester will be able to complete per day
Note on AK51: Stephen Connell (Contractor): This is the number of Test Cases each tester will be able to complete per day
Note on D62: Stephen Connell (Contractor): Number in minutes for a BA on average to complete test data creation for planned test cases submitted for manual or automation
Note on O62: Stephen Connell (Contractor): Number in minutes for a BA on average to complete test data creation for planned test cases submitted for manual or automation
Note on Z62: Stephen Connell (Contractor): Number in minutes for a BA on average to complete test data creation for planned test cases submitted for manual or automation
Note on AK62: Stephen Connell (Contractor): Number in minutes for a BA on average to complete test data creation for planned test cases submitted for manual or automation
Note on BG77: WICERS planned for Aug 6th are simple and medium complexity hence can be executed w/o addl FTE
Note on BH77: 2 WICERs (EPTM245, IPTM295) are planned to go Out of scope due to demantra upgrade. Waiting confirmation
Note on BN77: one of the WICER (WPTM111) will be combined with another WICER. Hence able to delivery with no addl FTE required
Note on BO77: 6 WICERS planned for Aug 14th are simple and medium complexity hence can be executed w/o addl FTE
Note on BQ77: 2 people (Karthik, Hari) are coming on Aug 15 (holiday) to do ground work for Aug 16th execution. So able to deliver w/o addl FTE
Note on BR77: all are report WICERS and able to achieve the target
Note on BU77: all are report WICERS and able to achieve the target
Note on BV77: all are report WICERS and able to achieve the target
Note on BW77: 3 WICER are reports 3 are new WICER hence need to strech this day to complete
Note on BX77: 5 WICERs are interface and data setup will be planned 3 days ahead with the help of GEM & Avinandhan. Hence able to complete this
Note on BY77: all are outbound interface, so able to complete 6 tc/FTE
Note on CB77: all are reports, able to deliver
Note on CC77: 22 Testcase are part of integeration, data setup with the help of Avinandhan will be done 3 days ahead. Hence able to complete the execution

## PivotSummary-RTR (hidden)
New/Retrofit/No code change required - Revised | (Multiple Items)
Gilead Code Drop Bucket | (Multiple Items)
Status | (Multiple Items)
Count of RICEW ID | Column Labels
Row Labels | 17-Jul | 18-Jul | 19-Jul | 20-Jul | 23-Jul | 24-Jul | 25-Jul | 26-Jul | 27-Jul | 30-Jul | 2-Aug | 3-Aug | 6-Aug | 9-Aug | 10-Aug | 13-Aug | 14-Aug | 16-Aug | 17-Aug | Grand Total
P1 |  | 1 | 1 |  |  |  |  | 1 |  | 1 | 1 |  | 2 | 2 | 1 |  | 1 |  |  | 11
P2 |  |  |  | 1 | [9 empty] | 3 | 1 |  |  |  |  | 5
P3 | 1 |  | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1 | 1 |  |  | 1 | 2 | 1 | 2 | 1 | 16
Grand Total | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 5 | 3 | 2 | 2 | 2 | 1 | 32
| 6 |  |  |  | 5 |  |  |  |  | 4 |  |  | 10 |  |  | 7